## data 260225
No. | Reference No. | Category | Description of Non-Conformance | Date Issued | Expected Reply Date | Actual Reply Date | Respond Period | Expected Completion Date | Closed Date | Status | NCR Aging from Expected Completion date | Closed NCR Effectiveness Verification Status | Package | Nature of NCR | Contractor | duration
1 | RTS-MRTS-PKG2A-ICQC-NCR-000005 | Quality | Deformed reinforcement result of poor welding quality | 2022-06-14 | 2022-06-28 | 2022-06-22 | Within 14 days | 2022-06-30 | 2022-08-17 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Nov'22 | PKG2A | Workmanship | APSB | 64
2 | RTS-MRTS-PKG2A-ICQC-NCR-000006 | Quality | 28 nos. of bored piles reinforcement cages installed, were not complying to the requirement of Design Criteria Subsection 900.5.10 (d) | 2022-06-14 | 2022-06-28 | 2022-06-23 | Within 14 days | 2022-09-16 | 2022-10-25 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG2A | Workmanship | APSB | 133
3 | RTS-MRTS-PKG2A-ICQC-NCR-000007 | Safety | It was found that the person in-charge (Radius Erpandar – AU256884) in electrical temporary work is not competent person. | 2022-06-30 | 2022-07-14 | 2022-07-15 | After 14 days | 2022-06-15 | 2022-07-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Nov'22 | PKG2A | Safety Control | APSB | 26
4 | RTS-MRTS-PKG2A-ICQC-NCR-000008 | Env | It was observed that the TSS reading for water sample taken from silt trap (ST04) is 436 mg/L by using TSS meter, which exceeded EIA approval condition limit, i.e., 50 mg/L. | 2022-06-30 | 2022-07-14 | 2022-07-15 | After 14 days | 2022-05-07 | 2022-07-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Nov'22 | PKG2A | TSS reading | APSB | 26
5 | RTS-MRTS-PKG2A-ICQC-NCR-000009 | Env | It was found that empty chemical containers stored inside Schedule Waste Storage with no labelling and Schedule Waste Records | 2022-06-30 | 2022-07-14 | 2022-07-15 | After 14 days | 2022-01-07 | 2022-07-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Nov'22 | PKG2A | Schedule waste management | APSB | 26
6 | RTS-MRTS-PKG2A-ICQC-NCR-000010 | Safety | crane maintenance record was not updated and verified | 2022-06-30 | 2022-07-14 | 2022-07-15 | After 14 days | 2022-05-31 | 2022-07-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Nov'22 | PKG2A | Machinery and equipment | APSB | 26
7 | RTS-MRTS-GENE-OVPR-NCR-000011 | Quality | Organization chart for Quality section does not reflect the resources planning as per requirement. | 2022-12-08 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-11-20 | 2023-01-06 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | GENE- | Manpower | APSB | 29
8 | RTS-MRTS-PKG3-VIAD-NCR-000012 | Quality | Found that the construction of trestle bridge has been carried out without approved document. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-09-20 | 2022-10-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG3- | Work without approved document | APSB | 52
9 | RTS-MRTS-PKG3-VIAD-NCR-000013 | Quality | Material submission made for trestle bridge steel column. The status is CODE 2. However, no record was found for material submission for the deck and steel beam that was erected at site. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-09-20 | 2022-10-18 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG3- | Work without approved document | APSB | 67
10 | RTS-MRTS-PKG3-VIAD-NCR-000014 | Quality | No record sighted for any training conducted for the construction of temporary trestle bridge works method statement in accordance to the General Specification requirement. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-09-20 | 2022-09-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG3- | Documentation | APSB | 49
11 | RTS-MRTS-PKG4-BUCS-NCR-000015 | Quality | It was found that testing work for Bi-Directional Load Test of PTP 1 & 2 have been carried out without approved method statement. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-09-25 | 2022-09-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG4- | Work without approved document | APSB | 49
12 | RTS-MRTS-PKG4-BUCS-NCR-000016 | Quality | During audit, it was found that the work near to KTMB area has been carried out without approved method statement. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-10-31 | 2022-11-15 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG4- | Work without approved document | APSB | 95
13 | RTS-MRTS-GENE-OVPR-NCR-000017 | Quality | it was observed that APSB has not appointed the Requirements Manager at the time of audit. The organization chart was reviewed but no Requirements Manager was included in the organization chart. | 2022-08-12 | 2022-08-26 | 2022-08-26 | Within 14 days | 2022-12-20 | 2022-12-01 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Manpower | APSB | 111
14 | RTS-MRTS-GENE-OVPR-NCR-000018 | Quality | During audit, it was observed that APSB has not appointed the RAMS Assurance Manager (RSAM) and RAMS Assurance Engineer (RSAE) at the time of audit. The organization chart was reviewed but no RAMS Assurance Manager or RAMS Assurance Engineer was included in the organization chart. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-12-15 | 2022-12-01 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Manpower | APSB | 111
15 | RTS-MRTS-GENE-OVPR-NCR-000019 | Quality | During audit, it was observed that APSB has yet to submit the RAMS Assurance Plan to the Employer at the time of audit. No RAMS Assurance Plan has been submitted. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-11-27 | 2022-11-15 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 95
16 | RTS-MRTS-GENE-OVPR-NCR-000020 | Quality | During audit, it was observed that APSB has yet to submit the Requirements Management Plan to the Employer at the time of audit. No Requirements Management Plan has been submitted. | 2022-08-12 | 2022-08-26 | 2022-08-23 | Within 14 days | 2022-11-27 | 2022-12-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 111
17 | RTS-MRTS-GENE-OVPR-NCR-000021 | Quality | During audit, it was observed that APSB has yet to develop the Requirements Management Database at the time of audit. No Requirements Management Database has been developed. | 2022-12-08 | 2022-08-26 | 2022-08-23 | Within 14 days | 2023-02-15 | 2023-02-23 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 77
18 | RTS-MRTS-PKG2A-ICQC-NCR-000022 | Env | TSS reading and Turbidity Reading taken exceeded EIA approval condition limit | 2022-08-19 | 2022-02-09 | 2022-08-30 | Within 14 days | 2022-08-30 | 2022-09-14 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG2A | TSS reading | APSB | 26
19 | RTS-MRTS-GENE-OVPR-NCR-000023 | Safety | CLQ Management Plan | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2023-02-28 | 2023-05-26 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | GENE- | Documentation | APSB | 350
20 | RTS-MRTS-GENE-OVPR-NCR-000024 | Env | Environmental Documentation – Environmental Management Plan (EMP) | 2022-06-10 | 2022-10-20 | 2022-10-13 | Within 14 days | 2023-01-15 | 2023-01-17 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 221
21 | RTS-MRTS-GENE-OVPR-NCR-000025 | Env | Environmental Management Plan (EMP) | 2022-06-10 | 2022-10-20 | 2022-11-11 | After 14 days | 2023-01-15 | 2023-01-27 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 231
22 | RTS-MRTS-GENE-OVPR-NCR-000026 | Safety | APSB Security Management Plan | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2022-10-29 | 2023-01-20 | Closed | Closed Late (>2 Months) | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 224
23 | RTS-MRTS-GENE-OVPR-NCR-000027 | Env | Environmental Documentation – Training, Promotion and Awareness | 2022-06-10 | 2022-10-20 | 2022-10-13 | Within 14 days | 2023-01-03 | 2023-02-24 | Closed | Closed on Time | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 259
24 | RTS-MRTS-GENE-OVPR-NCR-000028 | Env | Project Site Audit Findings (Environment) | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2022-12-30 | 2022-12-29 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Environment Control | APSB | 202
25 | RTS-MRTS-GENE-OVPR-NCR-000029 | Safety | No evidence of Site Safety Supervisor (SSS) has been hired by APSB as per GS requirements. | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2023-01-16 | 2023-03-21 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Aug'23 | GENE- | Manpower | APSB | 284
26 | RTS-MRTS-GENE-OVPR-NCR-000030 | Safety | Contractor’s Safety and Health Risk Assessment | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2022-10-29 | 2022-06-12 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 2
27 | RTS-MRTS-GENE-OVPR-NCR-000031 | Safety | Contractor’s Incident Notification, Investigation and Reporting Apps | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2023-03-15 | 2023-10-03 | Closed | Closed on Time | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 480
28 | RTS-MRTS-GENE-OVPR-NCR-000032 | Safety | APSB has not conducted any internal safety and health audit to their subcontractors and no internal audit procedure established as per requirement. | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2023-06-16 | 2023-03-08 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Internal process | APSB | 271
29 | RTS-MRTS-GENE-OVPR-NCR-000033 | Safety | Finding on Operational Safety and Health: | 2022-06-10 | 2022-10-20 | 2022-10-25 | After 14 days | 2023-06-16 | 2023-06-22 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Safety Control | APSB | 377
30 | RTS-MRTS-GENE-OVPR-NCR-000034 | Risk | During risk audit, APSB clarified that the Head of Risk was appointed as per the Org.chart. APSB has failed to provide evidence on the official appointment of the Head of Risk Department & Org. chart remained as Code 3. | 2022-10-18 | 2022-01-11 | 2022-01-11 | Within 14 days | 2022-11-15 | 2022-11-15 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Manpower | APSB | 28
31 | RTS-MRTS-GENE-OVPR-NCR-000035 | Risk | During risk audit, APSB has clarified that training on Risk Management has been conducted to their personnel on 27 September 2022. However, APSB has failed to provide evidence on the Risk Management Training Plan. | 2022-10-18 | 2022-01-11 | 2022-01-11 | Within 14 days | 2022-11-15 | 2022-11-15 | Closed | Closed on Time | Refer NCR Analysis May'23 | GENE- | Documentation | APSB | 28
32 | RTS-MRTS-GENE-OVPR-NCR-000036 | Safety | APSB failed to submit the proposed corrective actions within seven (7) days from the date of receipt of the SHE Inspection Report. | 2022-10-26 | 2022-09-11 | 2022-11-25 | After 14 days | 2023-02-13 | 2023-02-16 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Internal process | APSB | 113
33 | RTS-MRTS-PKG2A-ICQC-NCR-000037 | Env | water sample taken at the discharge point of ST04 exceeded the EIA Approval Condition permissible limit | 2022-09-11 | 2022-11-23 | 2022-11-23 | Within 14 days | 2022-12-25 | 2023-05-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG2A | TSS reading | APSB | 232
34 | RTS-MRTS-PKG6-WAHD-NCR-000038 | Env | no BMPs installed at the USM area and No protection installed at the public drain and USM area. | 2022-09-11 | 2022-11-23 | 2022-11-23 | Within 14 days | 2022-11-22 | 2022-12-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG6- | Environment Control | APSB | 109
35 | RTS-MRTS-PKG6-WAHD-NCR-000039 | Env | water sample taken at ST02 exceeded EIA Condition Approval permissible limit. | 2022-09-11 | 2022-11-23 | 2022-11-23 | Within 14 days | 2022-12-13 | 2022-12-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG6- | TSS reading | APSB | 109
36 | RTS-MRTS-PKG4-BUCS-NCR-000040 | Safety | Non conformance on lifting operation at Bukit Chagar Station | 2022-11-25 | 2022-09-12 | 2022-05-12 | Within 14 days | 2022-11-26 | 2022-12-08 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG4- | Machinery and equipment | APSB | 13
37 | RTS-MRTS-PKG3-VIAD-NCR-000041 | Env | traces of slurry spread and contaminate the sea | 2022-11-22 | 2022-06-12 | 2022-11-29 | Within 14 days | 2022-11-16 | 2022-12-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG3- | Environment Control | APSB | 37
38 | RTS-MRTS-PKG4-BUCS-NCR-000042 | Env | Oil spillage and oil trace from several machineries | 2022-11-22 | 2022-06-12 | 2022-02-12 | Within 14 days | 2023-01-17 | 2023-01-20 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG4- | Environment Control | APSB | 59
39 | RTS-MRTS-GENE-OVPR-NCR-000043 | P&D | Failed to submit Monthly Progress Report in time | 2022-11-21 | 2022-05-12 | 2022-05-12 | Within 14 days | 2023-05-04 | 2023-10-31 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 344
40 | RTS-MRTS-GENE-OVPR-NCR-000044 | P&D | Failed to submit Shedule of Design | 2022-11-25 | 2022-09-12 | 2022-10-12 | After 14 days | 2022-12-31 | 2024-02-23 | Closed | Closed Late (>2 Months) | Refer NCR Analysis June'24 | GENE- | Documentation | APSB | 455
41 | RTS-MRTS-PKG2A-ICQC-NCR-000045 | Env | It was observed schedule waste storage not maintained as per required. | 2022-01-12 | 2022-12-15 | 2022-12-19 | After 14 days | 2023-01-18 | 2023-01-20 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG2A | Schedule waste management | APSB | 373
42 | RTS-MRTS-PKG2A-ICQC-NCR-000046 | Safety | Unauthorised and unapproved machinery modification was observed on crawler crane | 2022-01-12 | 2022-12-15 | 2022-12-12 | Within 14 days | 2023-02-02 | 2023-01-20 | Closed | Closed on Time | Refer NCR Analysis May'23 | PKG2A | Machinery and equipment | APSB | 373
43 | RTS-MRTS-GENE-OVPR-NCR-000047 | Safety | Safety & Health Documentation - Clause G9.13 Incident Notification, Investigation and Reporting | 2022-08-12 | 2022-12-22 | 2022-12-17 | Within 14 days | 2023-08-02 | 2023-02-24 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 196
44 | RTS-MRTS-PKG6-WAHD-NCR-000048 | Env | murky water directly discharge to public drain | 2022-12-16 | 2022-12-30 | 2022-12-23 | Within 14 days | 2023-03-01 | 2023-06-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG6- | Environment Control | APSB | 167
45 | RTS-MRTS-PKG6-WAHD-NCR-000049 | Safety | Non conformance on excavation. piling and cofferdam works | 2022-12-16 | 2022-12-30 | 2022-12-21 | Within 14 days | 2023-11-01 | 2023-01-20 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG6- | Safety Control | APSB | 35
46 | RTS-MRTS-PKG6-WAHD-NCR-000050 | Safety | Non conformance on permit to work and pre task talk | 2022-12-16 | 2022-12-30 | 2022-12-21 | Within 14 days | 2022-12-22 | 2022-12-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis May'23 | PKG6- | Safety Control | APSB | 13
47 | RTS-MRTS-GENE-OVPR-NCR-000051 | Risk | No evidence of appointment of the risk personnel | 2022-12-28 | 2023-11-01 | 2023-06-01 | Within 14 days | 2023-03-22 | 2023-03-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | manpower | APSB | 92
48 | RTS-MRTS-GENE-OVPR-NCR-000052 | Safety | No CLQ Monthly Report was produced by APSB from Jan until Nov 22 | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-03-15 | 2023-03-21 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 62
49 | RTS-MRTS-GENE-OVPR-NCR-000053 | Env | Oil leakage under machine bored pile | 2023-01-18 | 2023-01-02 | 2023-01-31 | Within 14 days | 2023-02-13 | 2023-02-17 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Environment Control | APSB | 30
50 | RTS-MRTS-GENE-OVPR-NCR-000054 | Env | ENvironmental Aspect Impact register not established | 2023-01-18 | 2023-01-02 | 2023-01-31 | Within 14 days | 2023-02-27 | 2023-06-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Documentation | APSB | 136
51 | RTS-MRTS-PKG3-VIAD-NCR-000055 | Env | Failed to provide Early Warning System (EWS) | 2023-01-18 | 2023-01-02 | 2023-01-30 | Within 14 days | 2023-02-02 | 2023-09-02 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | PKG3- | Environment Control | APSB | 227
52 | RTS-MRTS-PKG6-WAHD-NCR-000056 | Env | TSS reading exceed permissible limit | 2023-01-18 | 2023-01-02 | 2023-01-30 | Within 14 days | 2023-06-02 | 2023-07-02 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | PKG6- | TSS reading | APSB | 165
53 | RTS-MRTS-PKG3-VIAD-NCR-000057 | Safety | Non conformity on hoisting and lifting operation | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-05-20 | 2023-10-03 | Closed | Closed on Time | Refer NCR Analysis Aug'23 | PKG3- | Safety Control | APSB | 258
54 | RTS-MRTS-GENE-OVPR-NCR-000058 | Safety | Non conformity on Site Safety and Health Committee | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-07-02 | 2023-02-21 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | GENE- | Safety Control | APSB | 34
55 | RTS-MRTS-GENE-OVPR-NCR-000059 | Safety | No evidence of HIRARC committee was established | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-02-20 | 2023-02-17 | Closed | Closed on Time | Refer NCR Analysis Aug'23 | GENE- | Safety Control | APSB | 30
56 | RTS-MRTS-GENE-OVPR-NCR-000060 | Safety | No evidence of appointment for Emergency Response Team member | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-03-16 | 2023-10-03 | Closed | Closed on Time | Refer NCR Analysis Aug'23 | GENE- | Environment control | APSB | 258
57 | RTS-MRTS-GENE-OVPR-NCR-000061 | Safety | Non conformity on Contractor training and competencies | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-02-06 | 2023-08-30 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | GENE- | Internal process | APSB | 224
58 | RTS-MRTS-GENE-OVPR-NCR-000062 | Safety | No evidence of safe working procedure established for high risk task | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-06-16 | 2023-11-21 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 307
59 | RTS-MRTS-GENE-OVPR-NCR-000063 | Safety | APSB failed to closed NCR issued within deadline | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-06-16 | 2023-10-27 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 282
60 | RTS-MRTS-PKG6-WAHD-NCR-000064 | Safety | Non conformity on Security Management Plan | 2023-01-18 | 2023-01-02 | 2023-01-02 | Within 14 days | 2023-02-03 | 2023-10-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | PKG6- | Documentation | APSB | 258
61 | RTS-MRTS-PKG3-VIAD-NCR-000007 | Quality | Pile cap precast panel post-concreting inspection | 2023-02-10 | 2023-02-24 | 2023-02-17 | Within 14 days | 2023-03-14 | 2023-03-21 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | PKG3- | Inspection | APSB | 39
62 | RTS-MRTS-PKG2A-ICQC-NCR-000011 | Safety | Non conformance for contractor's hoisting and lifting operations. | 2023-02-15 | 2023-01-03 | 2023-02-28 | Within 14 days | 2023-03-03 | 2023-03-07 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | PKG2A | Safety Control | APSB | 20
63 | RTS-MRTS-PKG2A-ICQC-NCR-000012 | Safety | Unsafe scaffold structure erected for Skid Tank | 2023-02-15 | 2023-01-03 | 2023-02-28 | Within 14 days | 2023-03-03 | 2023-05-25 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | PKG2A | Safety Control | APSB | 99
64 | RTS-MRTS-PKG6-WAHD-NCR-000008 | Safety | Cofferdam falsework | 2023-02-27 | 2023-03-13 | 2023-09-03 | Within 14 days | 2023-04-19 | 2023-04-28 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Aug'23 | PKG6- | Safety Control | APSB | 60
65 | RTS-MRTS-GENE-OVPR-NCR-000038 | Safety | No evidence of Sub-Contractor Security Management Plan submitted to APSB that can be provided by APSB. | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-06-20 | 2023-06-15 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | GENE- | Safety Control | APSB | 34
66 | RTS-MRTS-GENE-OVPR-NCR-000041 | Safety | Safety and Health Publicity and Promotion | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-09-06 | 2023-11-08 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Dec'23 | GENE- | Safety Control | APSB | 180
67 | RTS-MRTS-GENE-OVPR-NCR-000042 | Safety | Safety & Health Plan RTS-APSB-GENE-OVPR-PLN-000057 (Rev.00) was rejected on 13/09/2022. Revised SH plan submitted via email and commented by MRTS on 03/04/2023. No evidence for official submission of Safety & Health Plan. | 2023-05-12 | 2023-05-26 | 2023-05-25 | Within 14 days | 2023-01-07 | 2023-11-08 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Documentation | APSB | 180
68 | RTS-MRTS-GENE-OVPR-NCR-000043 | Safety | APSB failed to close the NCRs within the deadline stated in the NCR Response Sheet. The details of the NCR as follows: | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-06-30 | 2023-12-01 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 203
69 | RTS-MRTS-GENE-OVPR-NCR-000044 | Safety | No evidence of emergency drill conducted by APSB at least every 6 months. | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-08-17 | 2023-11-09 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Safety Control | APSB | 181
70 | RTS-MRTS-GENE-OVPR-NCR-000045 | Safety | In regard to MRTS Weekly SHE Inspection, APSB failed to submit the corrective action evidence within 7 days for the following report: | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-07-31 | 2023-12-01 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 203
71 | RTS-MRTS-GENE-OVPR-NCR-000046 | Safety | No evidence of APSB qualified personnel for high risk activities | 2023-12-05 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-06-30 | 2024-01-16 | Closed | Closed Late (>2 Months) | Refer NCR Analysis June'24 | GENE- | manpower | APSB | 42
72 | RTS-MRTS-PKG3-VIAD-NCR-000008 | Safety | Misuse of work permit. One (1) CCCC general worker work permit specified as ‘Cleaner’ (Mr.Dulal Munsi, Bangaldeshi). No evidence of SHE induction record. | 2023-05-12 | 2023-05-26 | 2023-05-25 | Within 14 days | 2023-09-30 | 2023-10-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG3- | Safety Control | APSB | 167
73 | RTS-MRTS-PKG6-WAHD-NCR-000009 | Safety | Findings on Scaffold Access / Cofferdam / Slope | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-06-30 | 2023-06-20 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG6- | Safety Control | APSB | 39
74 | RTS-MRTS-PKG6-WAHD-NCR-000010 | Safety | Lifting activity (concreting) by crawler crane PMA NO.: JH PMA 13392, 80T, Model: Kobelco 7080 was carried out at station with following non-compliances: | 2023-05-12 | 2023-05-26 | 2023-05-24 | Within 14 days | 2023-06-17 | 2023-06-20 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | PKG6- | Safety Control | APSB | 39
75 | RTS-MRTS-GENE-OVPR-NCR-000039 | Env | “Laporan Pemeriksaan BMPs” reported in ESC Online system due to 12.5mm rain event not within 24 hours. | 2023-05-12 | 2023-05-26 | 2023-05-23 | Within 14 days | 2023-05-29 | 2023-05-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Environment control | APSB | 19
76 | RTS-MRTS-GENE-OVPR-NCR-000040 | Env | Improper chemical storage and trace of spillage on the ground. | 2023-05-12 | 2023-05-26 | 2023-05-25 | Within 14 days | 2023-05-31 | 2023-07-27 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Environment control | APSB | 76
77 | RTS-MRTS-PKG4-BUCS-NCR-000005 | Env | No evidence of submission of written notification for genset DGS 1243 (125 kVA) at Bukit Chagar Station to DOE | 2023-05-12 | 2023-05-26 | 2023-05-23 | Within 14 days | 2023-05-29 | 2023-05-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | PKG4- | Documentation | APSB | 19
78 | RTS-MRTS-PKG4-BUCS-NCR-000006 | Safety | Cofferdam / False Work (Repetitive Issue – NCR Reference Number: RTS-MRTS-PKG6-WAHD-NCR-000008 & RTS- MRTS-PKG6-WAHD-NCR-000049) | 2023-05-12 | 2023-05-26 | 2023-05-26 | Within 14 days | 2023-06-30 | 2023-10-26 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | PKG4- | Safety Control | APSB | 167
79 | RTS-MRTS-GENE-OVPR-NCR-000047 | P&D | APSB has failed to close the Baseline Programme from Code 2 to Code 1 within 14 days and prolonged delay | 2023-05-12 | 2023-05-26 | 2023-05-24 | Within 14 days | 2023-06-30 | 2023-08-02 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | GENE- | Documentation | APSB | 82
80 | RTS-MRTS-GENE-OVPR-NCR-000048 | P&D | Non submission / close to Code 1 of Monthly progress report (MPR) | 2023-06-12 | 2023-06-26 | 2023-06-27 | After 14 days | 2023-12-09 | 2023-10-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 141
82 | RTS-MRTS-GENE-OVPR-NCR-000050 | Quality | PQP tracebility | 2023-07-07 | 2023-07-21 | 2023-07-21 | Within 14 days | 2023-10-20 | 2023-11-22 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Documentation | APSB | 138
83 | RTS-MRTS-PKG2A-ICQC-NCR-000014 | Quality | WIR report number was incorrectly referenced instead of using the MST/ITP reference number. | 2023-07-07 | 2023-07-21 | 2023-07-15 | Within 14 days | 2023-07-31 | 2023-11-09 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG2A | Documentation | APSB | 125
84 | RTS-MRTS-PKG3-VIAD-NCR-000009 | Quality | several debris were observed in the water, indicating a lack of proper maintenance and cleanliness in the area. | 2023-07-07 | 2023-07-21 | 2023-08-07 | Within 14 days | 2023-07-31 | 2023-08-08 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | PKG3- | Site cleanliness | APSB | 32
85 | RTS-MRTS-PKG3-VIAD-NCR-000010 | Quality | exposed rebar on the works area at P36 that may cause hazard and damage on the completed works. | 2023-07-07 | 2023-07-21 | 2023-08-07 | Within 14 days | 2023-07-31 | 2023-07-31 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG3- | Safety Control | APSB | 24
86 | RTS-MRTS-PKG3-VIAD-NCR-000011 | Quality | no document submission for the reinforcement bar that was made by Package 3 for a supplier from Ann Joo Metal Sdn Bh | 2023-07-07 | 2023-07-21 | 2023-07-20 | Within 14 days | 2023-08-31 | 2023-08-30 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG3- | Work without approved document | APSB | 54
87 | RTS-MRTS-PKG4-BUCS-NCR-000007 | Quality | there was no protection for the rebar storage area | 2023-07-07 | 2023-07-21 | 2023-07-13 | Within 14 days | 2023-09-15 | 2023-11-06 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG4- | Internal process | APSB | 122
88 | RTS-MRTS-PKG4-BUCS-NCR-000008 | Quality | no evidence found for the Welder competency certificate pertaining to the temporary works sheet pile and cofferdam. | 2023-07-07 | 2023-07-21 | 2023-07-13 | Within 14 days | 2023-08-15 | 2023-11-09 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG4- | Documentation | APSB | 125
89 | RTS-MRTS-PKG6-WAHD-NCR-000011 | Quality | it was found the master calibration list was not updated and found equipment calibration was already overdue | 2023-07-07 | 2023-07-21 | 2023-07-13 | Within 14 days | 2023-08-15 | 2023-09-05 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Internal process | APSB | 60
90 | RTS-MRTS-PKG6-WAHD-NCR-000012 | Quality | improper material storage practices | 2023-07-07 | 2023-07-21 | 2023-07-13 | Within 14 days | 2023-08-15 | 2023-11-22 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Internal process | APSB | 138
91 | RTS-MRTS-PKG6-WAHD-NCR-000013 | Quality | no post-concreting inspection has been conducted for the completed work | 2023-07-07 | 2023-07-21 | 2023-07-13 | Within 14 days | 2023-08-15 | 2023-09-05 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Inspection | APSB | 60
92 | RTS-MRTS-PKG5-VIAD-NCR-000003 | Safety | Unsafe lane closure due to SunCon’s trailer loaded with silo parked at Jalan Tun Abdul Razak | 2023-07-24 | 2023-07-08 | 2023-10-08 | After 14 days | 2023-08-15 | 2023-09-11 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Mar'24 | PKG5- | Traffic | SUNCON | 49
93 | RTS-MRTS-PKG5-VIAD-NCR-000001 | Env | Traces of oil was evident on the stagnant water in Zone 1B. | 2023-07-27 | 2023-10-08 | 2023-09-08 | Within 14 days | 2023-08-29 | 2023-08-25 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG5- | Environment control | SUNCON | 29
94 | RTS-MRTS-PKG5-VIAD-NCR-000004 | Env | Substandard storage of chemicals on site at Zone 1A and Zone 1B. | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-11-09 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Schedule waste management | SUNCON | 105
95 | RTS-MRTS-PKG5-VIAD-NCR-000005 | Env | Public road was seen with mud from the egress of the contractor’s work area. | 2023-07-27 | 2023-10-08 | 2023-09-08 | Within 14 days | 2023-08-29 | 2023-08-24 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG5- | Environment control | SUNCON | 28
96 | RTS-MRTS-PKG5-OVPR-NCR-000005 | Safety | contractor has failed to hire a Training Manager | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-09-14 | 2023-12-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Manpower | SUNCON | 135
97 | RTS-MRTS-PKG5-OVPR-NCR-000006 | Safety | no evidence of any measures to reduce the level of noise exposed to personnel | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-11-09 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Safety Control | SUNCON | 105
98 | RTS-MRTS-PKG5-OVPR-NCR-000007 | Safety | Delays in incident notification. Sunway Construction to notify the incident within 15 minutes however notification was received at 6.30pm. | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-08-30 | 2023-10-05 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG5- | Internal process | SUNCON | 70
99 | RTS-MRTS-PKG5-VIAD-NCR-000002 | Safety | observed the following non-conformities on lifting operations in Zone 1, | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-12-09 | 2023-12-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Safety Control | SUNCON | 135
100 | RTS-MRTS-PKG5-OVPR-NCR-000001 | Safety | SIte Security log book | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-08-29 | 2023-08-25 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG5- | Safety Control | SUNCON | 29
101 | RTS-MRTS-PKG5-OVPR-NCR-000002 | Safety | the Security Manager does not have the relevant qualification as per GS requirement. | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-08-23 | 2023-08-22 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG5- | manpower | SUNCON | 26
102 | RTS-MRTS-PKG5-OVPR-NCR-000003 | Safety | none of the security personnel interviewed at site have attended any form of security training related to construction site security | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-08-23 | 2023-08-22 | Closed | Closed on Time | Refer NCR Analysis Dec'23 | PKG5- | Internal process | SUNCON | 26
103 | RTS-MRTS-PKG5-OVPR-NCR-000004 | Safety | Traffic Management | 2023-07-27 | 2023-10-08 | 2023-10-08 | Within 14 days | 2023-09-14 | 2023-12-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Traffic | SUNCON | 135
104 | RTS-MRTS-PKG5-VIAD-NCR-000007 | Quality | Improper rebar stacking at storage yard Zone 1a. Rebar for pile cap was placed on the ground stacking with pier mould. | 2023-04-08 | 2023-08-18 | 2023-06-09 | After 14 days | 2023-09-13 | 2023-10-25 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG5- | Internal process | SUNCON | 200
105 | RTS-MRTS-PKG5-VIAD-NCR-000008 | Env | Fallen traffic cones and silt water overflowed onto the public road from construction site | 2023-07-08 | 2023-08-21 | 2023-10-08 | Within 14 days | 2023-11-09 | 2023-09-25 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG5- | Environment Control | SUNCON | 79
106 | RTS-MRTS-PKG5-VIAD-NCR-000006 | Safety | housekeeping conditions in Package 5 Zone 1 of the Sunway Construction area was deemed unsatisfactory. | 2023-07-08 | 2023-08-21 | 2023-10-08 | Within 14 days | 2023-08-17 | 2023-08-18 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Dec'23 | PKG5- | Safety Control | SUNCON | 41
107 | RTS-MRTS-GENE-OVPR-NCR-000054 | Safety | Unsuitable Material (USM) | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-11-09 | 2023-10-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Environment control | APSB | 69
108 | RTS-MRTS-GENE-OVPR-NCR-000053 | Safety | Security guard fail to provide security guard | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-08-28 | 2023-11-09 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Security | APSB | 79
109 | RTS-MRTS-PKG4-BUCS-NCR-000014 | Env | Fuel Burning Equipment | 2023-08-22 | 2023-05-09 | 2023-08-30 | Within 14 days | 2023-06-10 | 2023-11-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG4- | Environment control | APSB | 80
110 | RTS-MRTS-GENE-OVPR-NCR-000052 | Env | Erosion and Sedimentation Control Plan (ESCP) | 2023-08-22 | 2023-05-09 | 2023-01-09 | Within 14 days | 2023-07-09 | 2023-10-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | GENE- | Environment control | APSB | 65
111 | RTS-MRTS-GENE-OVPR-NCR-000051 | Env | Environmental Officer Duties | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-04-10 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | GENE- | Environment control | APSB | 79
112 | RTS-MRTS-PKG4-BUCS-NCR-000012 | Env | Oil Spillage at chemical storage | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-06-10 | 2023-11-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG4- | Environment control | APSB | 80
113 | RTS-MRTS-PKG4-BUCS-NCR-000011 | Safety | Temporary Access | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-09-30 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG4- | Safety Control | APSB | 79
114 | RTS-MRTS-PKG4-BUCS-NCR-000010 | Env | Handling and Storage of Hazardous Chemical and Flammable Material | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-09-30 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG4- | Schedule waste management | APSB | 79
115 | RTS-MRTS-PKG4-BUCS-NCR-000009 | Safety | Barricade, Cover to Voids, Trench, Bored Hole and Open Edges of Structure Access | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-09-30 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG4- | Safety Control | APSB | 79
116 | RTS-MRTS-PKG3-VIAD-NCR-000012 | Env | Dirty Public Road | 2023-08-22 | 2023-05-09 | 2023-08-30 | Within 14 days | 2023-02-10 | 2023-11-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG3- | Environment control | APSB | 80
117 | RTS-MRTS-ADV1A-OVPR-NCR-000002 | Safety | Non-compliance on CLQ Site Access | 2023-08-22 | 2023-05-09 | 2023-04-09 | Within 14 days | 2023-09-18 | 2023-11-09 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | ADV1A | Safety Control | APSB | 79
118 | RTS-MRTS-ADV1A-OVPR-NCR-000003 | Safety | it was observed that used of A Frame type scaffold at centralized Labour Quarters. | 2023-08-09 | 2023-09-22 | 2023-09-21 | Within 14 days | 2023-09-30 | 2023-11-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | ADV1A | Safety Control | APSB | 93
119 | RTS-MRTS-ADV1A-OVPR-NCR-000001 | Safety | it was observed that working platform used at centralized Labour Quarters was deemed unsatisfactory. | 2023-08-09 | 2023-09-22 | 2023-09-21 | Within 14 days | 2023-09-30 | 2023-11-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | ADV1A | Safety Control | APSB | 93
120 | RTS-MRTS-GENE-OVPR-NCR-000056 | Env | Chemical Health Risk Assessment (CHRA) | 2023-09-19 | 2023-03-10 | 2023-03-10 | Within 14 days | 2023-11-30 | 2024-02-27 | Closed | Closed Late (>2 Months) | Refer NCR Analysis June'24 | GENE- | Environment control | APSB | 161
121 | RTS-MRTS-PKG3-VIAD-NCR-000013 | Env | Noise Exposure Assessment | 2023-09-19 | 2023-03-10 | 2023-03-10 | Within 14 days | 2023-11-30 | 2023-12-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG3- | Environment control | APSB | 73
122 | RTS-MRTS-PKG6-WAHD-NCR-000015 | Env | Direct Discharge | 2023-09-19 | 2023-03-10 | 2023-09-25 | Within 14 days | 2023-09-10 | 2023-12-10 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Environment control | APSB | 82
123 | RTS-MRTS-PKG6-WAHD-NCR-000014 | Env | Oil Spillage from machineries not managed as schedule waste | 2023-09-19 | 2023-03-10 | 2023-02-10 | Within 14 days | 2023-10-16 | 2023-10-19 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Environment control | APSB | 30
124 | RTS-MRTS-PKG5-VIAD-NCR-000009 | Safety | potholes in the contractor's ROW, the road was not maintained as per TMP (Traffic Management Plan) and public safety requirements. | 2023-09-25 | 2023-09-10 | 2023-09-10 | Within 14 days | 2023-10-13 | 2023-10-13 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Traffic | SUNCON | 18
125 | RTS-MRTS-PKG6-WAHD-NCR-000016 | Safety | security post Depot Wadi Hana main entrance it was observed that Security post without lighting and electrical supply. | 2023-10-05 | 2023-10-19 | 2023-11-10 | Within 14 days | 2023-11-10 | 2023-11-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG6- | Security | APSB | 27
126 | RTS-MRTS-PKG5-VIAD-NCR-000011 | Env | during heavy rain, the surface water runoff flowed out from the Site into Jalan Ismail Sultan (Protocol Road). | 2023-04-10 | 2023-10-18 | 2023-10-14 | Within 14 days | 2023-10-20 | 2023-06-11 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG5- | Environment control | SUNCON | 62
127 | RTS-MRTS-PKG5-VIAD-NCR-000012 | Safety | Workers used illegal access (red tagged) during the dismantling of the pier mold and access is in the process of being extended. | 2023-03-10 | 2023-10-17 | 2023-10-16 | Within 14 days | 2023-10-27 | 2023-10-26 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Safety Control | SUNCON | 230
128 | RTS-MRTS-PKG3-VIAD-NCR-000014 | Safety | The temporary toilet was placed at the edge of the bridge and evidence of green algae at the bottom of the temporary toilet. | 2023-03-10 | 2023-10-17 | 2023-12-10 | Within 14 days | 2023-10-26 | 2023-10-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG3- | Safety Control | APSB | 234
129 | RTS-MRTS-PKG3-VIAD-NCR-000015 | Safety | The Emergency spill kit (sand) were found full with water and not effective to absorb the spillage. The container shall be covered and the sand are not overflow from the container. | 2023-03-10 | 2023-10-17 | 2023-09-10 | Within 14 days | 2023-10-23 | 2023-10-26 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Mar'24 | PKG3- | Environment control | APSB | 230
130 | RTS-MRTS-PKG5-VIAD-NCR-000010 | Quality | MSA embedded PVC pipe sleeve used for tie rod pier mould not submitted. | 2023-03-10 | 2023-10-17 | 2023-10-16 | Within 14 days | 2023-10-23 | 2024-05-15 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Documentation | SUNCON | 432
131 | RTS-MRTS-PKG5-VIAD-NCR-000014 | Safety | non-conformities for traffic management and public safety at Zone 3 | 2023-10-16 | 2023-10-30 | 2023-10-19 | Within 14 days | 2023-07-11 | 2023-11-06 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Traffic | SUNCON | 21
132 | RTS-MRTS-PKG4-BUCS-NCR-000015 | Env | non - compliance on the chemical management | 2023-10-17 | 2023-10-31 | 2023-10-25 | Within 14 days | 2023-08-11 | 2023-11-07 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG4- | Environment control | APSB | 21
133 | RTS-MRTS-PKG5-VIAD-NCR-000015 | Env | Erosion and Sedimentation Control Plan (ESCP) and Waste Management No maintenance of BMPs and cleaning of road drainage. | 2023-10-16 | 2023-10-30 | 2023-01-11 | After 14 days | 2023-11-17 | 2023-11-17 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Environment control | SUNCON | 32
134 | RTS-MRTS-PKG5-VIAD-NCR-000013 | Safety | non-conformities for Pile Cap Cofferdam P29, P30 and P31 NB Zone 3 | 2023-10-16 | 2023-10-30 | 2023-10-21 | Within 14 days | 2023-11-24 | 2023-11-17 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Safety Control | SUNCON | 32
135 | RTS-MRTS-PKG6-WAHD-NCR-000017 | Safety | discovered that shuttering formwork inside riser activity located at gridline DD12/DD13 were not comply with the confined space requirement | 2023-10-30 | 2023-11-13 | 2023-07-11 | Within 14 days | 2023-11-14 | 2024-03-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG6- | Safety Control | APSB | 123
136 | RTS-MRTS-PKG5-VIAD-NCR-000017 | Env | water discharged from the wheel washing activity at the Fabrication Yard (Zone 2) flowed directly into a public drain. | 2023-07-11 | 2023-11-21 | 2023-11-14 | Within 14 days | 2023-11-21 | 2023-11-16 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Environment control | SUNCON | 128
137 | RTS-MRTS-PKG5-VIAD-NCR-000016 | Env | observed traces of tyre marks from site entrance going into Jalan Ismail Sultan (Protocol Road). | 2023-07-11 | 2023-11-21 | 2023-11-14 | Within 14 days | 2023-11-21 | 2023-11-16 | Closed | Closed on Time | Refer NCR Analysis Mar'24 | PKG5- | Environment control | SUNCON | 128
138 | RTS-MRTS-PKG6-WAHD-NCR-000018 | Safety | Roofing installation located at TNB substation were not comply with the WAH requirement . not attend blue and grey card | 2023-11-16 | 2023-11-30 | 2023-11-27 | Within 14 days | 2023-12-31 | 2024-03-01 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG6- | Safety Control | APSB | 106
139 | RTS-MRTS-PKG5-VIAD-NCR-000019 | Quality | Pile cap backfilling materials used on site without MSA approval evidence. | 2023-11-15 | 2023-11-29 | 2023-11-24 | Within 14 days | 2023-12-20 | 2024-05-15 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Work without approved document | SUNCON | 182
140 | RTS-MRTS-PKG6-WAHD-NCR-000020 | Env | non-compliance for water discharge at Silt Trap 1 (ST1). The reading of the water discharge as per details below: | 2023-11-24 | 2023-08-12 | 2023-04-12 | Within 14 days | 2023-12-20 | 2024-01-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG6- | TSS reading | APSB | 68
141 | RTS-MRTS-PKG6-WAHD-NCR-000019 | Env | Best Management Practices (BMPs) for erosion and sediment control not installed and maintained as per required. | 2023-11-24 | 2023-08-12 | 2023-05-12 | Within 14 days | 2024-01-17 | 2024-01-15 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG6- | Environment control | APSB | 52
142 | RTS-MRTS-PKG3-VIAD-NCR-000016 | Safety | no evidence of crane operator attending Grey Card training under SHE Passport Scheme for Machinery Operators | 2023-11-24 | 2023-08-12 | 2023-12-22 | After 14 days | 2024-02-29 | 2024-02-27 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG3- | Safety Control | APSB | 95
143 | RTS-MRTS-ADV1A-OVPR-NCR-000004 | Env | Oil spillage from genset not managed as scheduled waste. | 2023-11-24 | 2023-08-12 | 2023-11-30 | Within 14 days | 2024-12-01 | 2024-05-02 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | ADV1A | Environment control | APSB | 160
144 | RTS-MRTS-PKG5-VIAD-NCR-000024 | Quality | Sheet piling works proceed without approval from Supervising Consultant for P16. | 2023-08-12 | 2023-12-22 | 2024-08-01 | After 14 days | 2024-01-31 | 2024-03-22 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Work without approved document | SUNCON | 223
145 | RTS-MRTS-PKG5-VIAD-NCR-000023 | Quality | No piloting work for sheet pile installation at P33. | 2023-08-12 | 2023-12-22 | 2024-08-01 | After 14 days | 2024-01-31 | 2024-03-22 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Internal process | SUNCON | 223
146 | RTS-MRTS-PKG4-BUCS-NCR-000018 | Safety | no Emergency Preparedness and Responses Plan at mezzanine area. | 2023-08-12 | 2023-12-22 | 2023-12-20 | Within 14 days | 2023-12-31 | 2024-01-16 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG4- | Safety Control | APSB | 157
147 | RTS-MRTS-PKG4-BUCS-NCR-000017 | Env | Wheel washing facilities provided but ineffective | 2023-06-12 | 2023-12-20 | 2023-12-19 | Within 14 days | 2024-01-15 | 2024-01-16 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG4- | Environment Control | APSB | 218
148 | RTS-MRTS-PKG5-VIAD-NCR-000021 | Safety | activity Hand dug caisson at CBP 6 were not comply with the confine space requirement | 2023-05-12 | 2023-12-19 | 2023-12-18 | Within 14 days | 2024-05-01 | 2024-03-01 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Safety Control | SUNCON | 294
149 | RTS-MRTS-PKG5-VIAD-NCR-000020 | Safety | Rebar installation did not conform with the Safety requirement | 2023-05-12 | 2023-12-19 | 2023-12-15 | Within 14 days | 2024-05-01 | 2024-03-01 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Safety Control | SUNCON | 294
150 | RTS-MRTS-PKG5-VIAD-NCR-000022 | Env | inadequate drainage (downstream) provisions located at P1d. The earth drain is not channelled into any BMPs before discharging into receiving waterways. | 2023-05-12 | 2023-12-19 | 2023-12-12 | Within 14 days | 2024-10-01 | 2024-04-01 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Environment Control | SUNCON | 325
151 | RTS-MRTS-PKG5-OVPR-NCR-000009 | Safety | opening between Pier P1d1 and P1c. There shall be no opening at hoardings and to protect the public from enter the construction site. | 2023-04-12 | 2023-12-18 | 2023-12-15 | Within 14 days | 2024-01-19 | 2024-01-16 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Security | SUNCON | 279
152 | RTS-MRTS-PKG4-BUCS-NCR-000016 | Safety | No power supply at security post. | 2023-04-12 | 2023-12-18 | 2023-12-13 | Within 14 days | 2024-01-19 | 2024-01-19 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG4- | Security | APSB | 282
153 | RTS-MRTS-PKG5-VIAD-NCR-000025 | Quality | Non-compliance of F3 surface finishes as per M&W specification requirement. | 2023-12-22 | 2024-05-01 | 2024-01-01 | Within 14 days | 2024-01-20 | 2024-05-15 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Sep'24 | PKG5- | workmanship | SUNCON | 145
154 | RTS-MRTS-PKG5-VIAD-NCR-000026 | Quality | Sheet pile alignment clashed with P3 pile cap | 2023-12-27 | 2024-10-01 | 2024-01-22 | After 14 days | 2024-05-02 | 2024-07-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | workmanship | SUNCON | 189
155 | RTS-MRTS-PKG4-BUCS-NCR-000019 | Env | Substandard chemical storage. Traces of oil spillage from secondary containment, Oil spillage around chemical storage not handled as scheduled waste | 2023-12-28 | 2024-11-01 | 2024-08-01 | Within 14 days | 2024-01-29 | 2024-04-18 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Sep'24 | PKG4- | Environment Control | APSB | 112
156 | RTS-MRTS-PKG2A-OVPR-NCR-000001 | Env | Slope Integrity and design check for slope stability is unavailable upon request. | 2024-01-11 | 2024-01-25 | 2024-01-24 | Within 14 days | 2024-06-02 | 2024-02-06 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG2A(IJM) | Environment Control | IJMC | 26
157 | RTS-MRTS-PKG2A-OVPR-NCR-000002 | Env | Surface Runoffs | 2024-01-11 | 2024-01-25 | 2024-12-01 | Within 14 days | 2024-01-31 | 2024-01-31 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG2A(IJM) | Environment Control | IJMC | 20
158 | RTS-MRTS-PKG5-VIAD-NCR-000029 | Safety | Non-conformities were observed in Cofferdam | 2024-01-05 | 2024-01-19 | 2024-01-13 | Within 14 days | 2024-01-26 | 2024-01-19 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Safety Control | SUNCON | 14
159 | RTS-MRTS-PKG5-VIAD-NCR-000032 | P&D | Non Submission / Close to Code 1 of Monthly Progress Report (MPR) | 2024-05-01 | 2024-01-19 | 2024-04-03 | After 14 days | 2024-03-25 | 2024-05-11 | Closed | Closed Late (>2 Months) | 2025-03-02 | PKG5- | Documentation | SUNCON | 10
160 | RTS-MRTS-PKG5-VIAD-NCR-000039 | Risk | Non Submission of Risk Management Checklist | 2024-01-12 | 2024-01-26 | 2024-05-25 | After 14 days | 2024-07-06 | 2024-07-01 | Closed | Closed Late (<2 Months) | 2024-09-29 | PKG5- | Documentation | SUNCON | 171
161 | RTS-MRTS-PKG5-VIAD-NCR-000038 | Risk | Non Submission of Monthly Risk Management Report | 2024-01-12 | 2024-01-26 | 2024-05-25 | After 14 days | 2024-07-06 | 2024-07-01 | Closed | Closed Late (<2 Months) | 2024-09-29 | PKG5- | Documentation | SUNCON | 171
162 | RTS-MRTS-PKG5-VIAD-NCR-000037 | Risk | Lack of information on lesson learnt from other Rail Lines Projects | 2024-01-12 | 2024-01-26 | 2024-05-25 | After 14 days | 2024-07-06 | 2024-08-08 | Closed | Closed Late (>2 Months) | 2024-06-11 | PKG5- | Documentation | SUNCON | 209
163 | RTS-MRTS-PKG5-VIAD-NCR-000036 | Risk | Non Submission of Risk Management Structure | 2024-01-12 | 2024-01-26 | 2024-05-25 | After 14 days | 2024-07-06 | 2024-08-08 | Closed | Closed Late (>2 Months) | 2024-06-11 | PKG5- | Documentation | SUNCON | 209
164 | RTS-MRTS-PKG5-VIAD-NCR-000035 | Risk | Non Competencies Head of Risk Department | 2024-01-12 | 2024-01-26 | 2024-04-26 | After 14 days | 2024-05-05 | 2024-11-06 | Closed | Closed Late (<2 Months) | 2024-09-09 | PKG5- | Manpower | SUNCON | 299
165 | RTS-MRTS-PKG5-VIAD-NCR-000034 | Risk | Non Submission of Risk Management Policy | 2024-01-12 | 2024-01-26 | 2024-04-26 | After 14 days | 2024-05-05 | 2024-11-06 | Closed | Closed Late (<2 Months) | 2024-09-09 | PKG5- | Documentation | SUNCON | 299
166 | RTS-MRTS-PKG5-VIAD-NCR-000033 | Risk | Non Submission of Risk Management Framework (RMF) | 2024-01-12 | 2024-01-26 | 2024-04-26 | After 14 days | 2024-05-05 | 2024-05-30 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Documentation | SUNCON | 139
167 | RTS-MRTS-PKG2A-OVPR-NCR-000004 | Safety | IJMC failed Appoint Safety & Health Training Manager | 2024-01-17 | 2024-01-31 | 2024-02-28 | After 14 days | 2024-03-31 | 2024-06-13 | Closed | Closed Late (>2 Months) | 2024-11-09 | PKG2A(IJM) | Manpower | IJMC | 148
168 | RTS-MRTS-PKG2A-OVPR-NCR-000003 | Safety | IJMC failed Appoint of CLQ Manager | 2024-01-17 | 2024-01-31 | 2024-08-02 | After 14 days | 2024-04-30 | 2024-06-13 | Closed | Closed Late (<2 Months) | 2024-11-09 | PKG2A(IJM) | Manpower | IJMC | 148
169 | RTS-MRTS-PKG5-VIAD-NCR-000040 | Safety | Traffic Management - SBG Launching | 2024-01-16 | 2024-01-30 | 2024-04-16 | After 14 days | 2024-04-23 | 2024-05-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Traffic | SUNCON | 136
170 | RTS-MRTS-PKG5-VIAD-NCR-000031 | Quality | Non-Compliance of Formwork Removal at Pilecap P19 | 2024-01-18 | 2024-01-02 | 2024-05-02 | After 14 days | 2024-02-29 | 2024-05-15 | Closed | Closed Late (>2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Workmanship | SUNCON | 118
171 | RTS-MRTS-PKG5-VIAD-NCR-000030 | Quality | Non-Compliance of Modified Temporary Strutting Cofferdam P30SB | 2024-01-18 | 2024-01-02 | 2024-05-02 | After 14 days | 2024-02-29 | 2024-07-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Workmanship | SUNCON | 167
172 | RTS-MRTS-PKG5-VIAD-NCR-000028 | Quality | Insufficient starter bar for bored pile P6NB-1 | 2024-01-22 | 2024-05-02 | 2024-05-02 | Within 14 days | 2024-02-24 | 2024-07-03 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Workmanship | SUNCON | 163
173 | RTS-MRTS-PKG5-VIAD-NCR-000027 | Quality | Materials placed on PUB pipeline alignment | 2024-01-22 | 2024-05-02 | 2024-03-18 | After 14 days | 2024-03-31 | 2024-04-18 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Internal process | SUNCON | 87
174 | RTS-MRTS-PKG6-WAHD-NCR-000021 | Quality | Improper stacking and rusty rebar at Fabrication Yard | 2024-01-19 | 2024-02-02 | 2024-01-29 | Within 14 days | 2024-02-29 | 2024-07-11 | Closed | Closed Late (>2 Months) | 2025-05-02 | PKG6- | Internal process | APSB | 174
175 | RTS-MRTS-PKG4-BUCS-NCR-000020 | Quality | Improper stacking and rusty rebar at Fabrication Yard | 2024-01-19 | 2024-02-02 | 2024-01-29 | Within 14 days | 2024-02-29 | 2024-04-17 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG4- | Internal process | APSB | 89
176 | RTS-MRTS-PKG5-VIAD-NCR-000041 | Safety | Hand Dug Caisson Pile, P1R and P1L | 2024-02-09 | 2024-02-23 | 2024-02-19 | Within 14 days | 2024-01-03 | 2024-03-01 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG5- | Safety Control | SUNCON | 21
177 | RTS-MRTS-PKG4-BUCS-NCR-000025 | Env | non-compliances regarding waste management | 2024-02-09 | 2024-02-23 | 2024-02-20 | Within 14 days | 2024-03-29 | 2024-03-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG4- | Schedule waste management | APSB | 49
178 | RTS-MRTS-PKG2A-ICQC-NCR-000015 | Quality | Poor workmanship of welding works at SP: 90. | 2024-02-09 | 2024-02-21 | 2024-07-02 | Within 14 days | 2024-02-14 | 2024-02-21 | Closed | Closed Late (<2 Months) | Refer NCR Analysis June'24 | PKG2A(IJM) | Workmanship | IJMC | 12
179 | RTS-MRTS-PKG6-WAHD-NCR-000025 | Quality | Staircase ES WAHD 02 at Gridline D2/DC respectively are not constructed in accordance to the IFC Drawings. | 2024-01-02 | 2024-02-15 | 2024-02-17 | After 14 days | 2024-03-20 | 2025-01-20 | Closed | Closed Late (>2 Months) |  | PKG6- | Work constructed not per drawing | APSB | 384
180 | RTS-MRTS-PKG6-WAHD-NCR-000024 | Quality | Staircase ES WAHD 01 at Gridline DA/D1 is not constructed in accordance to the IFC Drawings. | 2024-01-02 | 2024-02-15 | 2024-02-17 | After 14 days | 2024-03-20 | 2025-01-20 | Closed | Closed Late (>2 Months) |  | PKG6- | Work constructed not per drawing | APSB | 384
181 | RTS-MRTS-PKG4-BUCS-NCR-000024 | Quality | The position of WC at BUCS TNB Toilet is not constructed in accordance to the IFC Drawings | 2024-01-02 | 2024-02-15 | 2024-02-21 | After 14 days | 2024-03-20 | 2024-08-22 | Closed | Closed Late (>2 Months) | 2024-11-20 | PKG4- | Work constructed not per drawing | APSB | 233
182 | RTS-MRTS-PKG4-BUCS-NCR-000023 | Quality | Concrete bulging appears along RC Beam B1B1(400x1000) at TNB Roof Level SSL +115.45m at Gridline SB/S3 | 2024-01-02 | 2024-02-15 | 2024-02-15 | Within 14 days | 2024-02-29 | 2024-08-22 | Closed | Closed Late (>2 Months) | 2024-11-20 | PKG4- | Workmanship | APSB | 233
183 | RTS-MRTS-PKG4-BUCS-NCR-000029 | Safety | Only 1 Lookout was available at site. | 2024-02-09 | 2024-02-23 | 2024-02-20 | Within 14 days | 2024-02-29 | 2024-02-27 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG4- | Safety Control | APSB | 18
184 | RTS-MRTS-PKG4-BUCS-NCR-000028 | Safety | non-compliance on the Hoisting and Lifting Operations. | 2024-02-09 | 2024-02-23 | 2024-02-21 | Within 14 days | 2024-05-04 | 2024-03-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG4- | Machinery and equipment | APSB | 49
185 | RTS-MRTS-PKG4-BUCS-NCR-000027 | Safety | There is a non-compliance on the Plant, Equipment and Vehicle. Damage excavator track | 2024-02-09 | 2024-02-23 | 2024-02-20 | Within 14 days | 2024-02-29 | 2024-02-29 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG4- | Machinery and equipment | APSB | 20
186 | RTS-MRTS-GENE-OVPR-NCR-000063 | Quality | SA Audit: Not yet closed one finding (ref: RTS-APSB-OBS-QUA-GEN-000009) from the audit since March 2023 | 2024-02-14 | 2024-02-28 | 2024-04-04 | After 14 days | 2024-01-04 | 2024-05-04 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | GENE- | Documentation | APSB | 80
187 | RTS-MRTS-PKG4-BUCS-NCR-000026 | Safety | non-compliance on the Scaffold and falsework. | 2024-02-20 | 2024-05-03 | 2024-02-27 | Within 14 days | 2024-08-03 | 2024-03-01 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG4- | Safety Control | APSB | 10
188 | RTS-MRTS-PKG5-VIAD-NCR-000042 | Quality | Honeycomb in concrete and rebar expose observed and Rust stain on 2 side of pier head concrete surface. | 2024-02-19 | 2024-04-03 | 2024-02-23 | Within 14 days | 2024-07-03 | 2024-06-25 | Closed | Closed Late (>2 Months) | 2024-09-23 | PKG5- | Workmanship | SUNCON | 127
189 | RTS-MRTS-PKG2A-ICQC-NCR-000017 | Env | Slope Integrity: Visible slope collapsed at the slope incline | 2024-02-16 | 2024-01-03 | 2024-02-22 | Within 14 days | 2024-10-03 | 2024-02-28 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG2A(IJM) | Environment Control | IJMC | 12
190 | RTS-MRTS-PKG2A-ICQC-NCR-000016 | Env | Construction Materials Placed Directly on temporary sandbag barrier | 2024-02-16 | 2024-01-03 | 2024-02-21 | Within 14 days | 2024-02-26 | 2024-02-23 | Closed | Closed on Time | Refer NCR Analysis June'24 | PKG2A(IJM) | Environment Control | IJMC | 7
191 | RTS-MRTS-PKG4-BUCS-NCR-000030 | Env | Murky Water Discharge to KTMB Drainage | 2024-02-27 | 2024-12-03 | 2024-11-03 | Within 14 days | 2024-01-04 | 2024-03-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG4- | Environment Control | APSB | 31
192 | RTS-MRTS-PKG5-VIAD-NCR-000043 | Safety | non-conformities were observed during the construction of piers in Zone 1a and Zone 3, P | 2024-02-27 | 2024-12-03 | 2024-05-03 | Within 14 days | 2024-03-26 | 2024-03-21 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Safety Control | SUNCON | 23
193 | RTS-MRTS-PKG5-VIAD-NCR-000044 | Safety | no provision of SUNCON has conducted a 3rd Party Safety and Health Audit within 6 months | 2024-02-27 | 2024-12-03 | 2024-01-02 | Within 14 days | 2024-04-30 | 2024-07-06 | Closed | Closed Late (<2 Months) | 2024-05-09 | PKG5- | Internal process | SUNCON | 130
194 | RTS-MRTS-PKG3-VIAD-NCR-000018 | Quality | Method Statement Rectification Works for SBG Structural Damage at Span P35 – P36 with ref: RTS-APSB-PKG3-OVPR-MST-000038 still in Code 3. | 2024-02-28 | 2024-03-13 | 2024-07-03 | Within 14 days | 2024-03-25 | 2024-04-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG3- | Documentation | APSB | 61
195 | RTS-MRTS-PKG6-WAHD-NCR-000026 | Safety | NCR CHESS - NO Fall Prevention System in place | 2024-03-18 | 2024-01-04 | 2024-01-04 | Within 14 days | 2024-05-31 | 2024-05-31 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG6- | Safety Control | APSB | 74
196 | RTS-MRTS-PKG5-VIAD-NCR-000052 | Env | NCR CHESS - Surface Runoff Water | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-03-05 | 2024-05-02 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Environment Control | SUNCON | 44
197 | RTS-MRTS-PKG5-VIAD-NCR-000049 | Env | NCR CHESS - Submission of Monthly Environmental Monitoring Report (MEMR) January 2024 | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-06-04 | 2024-05-04 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Documentation | SUNCON | 46
198 | RTS-MRTS-PKG5-VIAD-NCR-000050 | Env | NCR CHESS - Scheduled Waste | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-04-26 | 2024-04-25 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Schedule waste management | SUNCON | 37
199 | RTS-MRTS-PKG5-VIAD-NCR-000046 | Env | yet to conduct assessment for chemical being used and stored at site and Chemical Hazard Risk Assessment (CHRA) report is not available. | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-04-26 | 2024-04-25 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Environment Control | SUNCON | 37
200 | RTS-MRTS-PKG5-VIAD-NCR-000045 | Safety | SAFETY - NCR AUDIT Q1 - Working at Height | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-12-04 | 2024-04-18 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Safety Control | SUNCON | 30
201 | RTS-MRTS-PKG5-VIAD-NCR-000047 | Env | NCR CHESS SAFETY AUDIT Q1 - Handling and Storage of Hazardous Chemical And Flammable Material | 2024-03-19 | 2024-02-04 | 2024-02-04 | Within 14 days | 2024-04-19 | 2024-04-18 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Environment Control | SUNCON | 30
202 | RTS-MRTS-PKG5-VIAD-NCR-000048 | Safety | CHESS NCR SAFETY AUDIT Q1 - Centralized Labour Quarters | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-05-04 | 2024-04-18 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Safety Control | SUNCON | 30
203 | RTS-MRTS-PKG5-VIAD-NCR-000051 | Env | NCR CHESS - Chemical Management | 2024-03-19 | 2024-02-04 | 2024-03-29 | Within 14 days | 2024-04-26 | 2024-04-25 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Environment Control | SUNCON | 37
204 | RTS-MRTS-PKG3-VIAD-NCR-000019 | Quality | Shear Connector for Trackwork at P46 Long Span | 2024-03-20 | 2024-03-04 | 2024-03-23 | Within 14 days | 2024-06-30 | 2024-12-13 | Closed | Closed Late (>2 Months) | 2025-03-13 | PKG3- | Workmanship | APSB | 268
205 | RTS-MRTS-PKG3-VIAD-NCR-000020 | Quality | Damaged SBG ( ID no: RTS - SBG - P43-P44- S1 - 13, cast on 4 March 2024) | 2024-03-20 | 2024-03-04 | 2024-03-23 | Within 14 days | 2024-04-30 | 2024-04-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG3- | Workmanship | APSB | 40
206 | RTS-MRTS-PKG5-VIAD-NCR-000053 | Quality | NCR at Pile Cap Cofferdam - Pier 10, Zone 2 | 2024-03-20 | 2024-03-04 | 2024-04-30 | After 14 days | 2024-10-05 | 2024-12-08 | Closed | Closed Late (>2 Months) | 2024-10-11 | PKG5- | Workmanship | SUNCON | 263
207 | RTS-MRTS-PKG2A-ICQC-NCR-000018 | Safety | NCR CHESS - Hoisting and Lifting Operation (Backhoe) | 2024-03-21 | 2024-04-04 | 2024-04-23 | After 14 days | 2024-04-30 | 2024-05-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Safety Control | IJMC | 71
208 | RTS-MRTS-PKG2A-ICQC-NCR-000019 | Env | NCR CHESS - Handling and Storage of Chemical | 2024-03-21 | 2024-04-04 | 2024-04-23 | After 14 days | 2024-04-26 | 2024-05-31 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Environment Control | IJMC | 71
210 | RTS-MRTS-PKG2A-ICQC-NCR-000021 | Safety | NCR CHESS - Hoisting and Lifting Operations (Crawler Crane) | 2024-03-21 | 2024-04-04 | 2024-05-30 | After 14 days | 2024-06-13 | 2024-09-18 | Closed | Closed Late (>2 Months) | 2024-12-17 | PKG2A(IJM) | Safety Control | IJMC | 181
211 | RTS-MRTS-PKG2A-ICQC-NCR-000022 | Safety | NCR CHESS - Temporary Works (Cofferdam No.1) | 2024-03-21 | 2024-04-04 | 2024-01-07 | After 14 days | 2024-07-15 | 2024-09-18 | Closed | Closed Late (>2 Months) | 2024-12-17 | PKG2A(IJM) | Documentation | IJMC | 181
212 | RTS-MRTS-PKG2A-ICQC-NCR-000023 | Safety | NCR CHESS - Contractor’s Site Personnel | 2024-03-21 | 2024-04-04 | 2024-05-30 | After 14 days | 2024-06-14 | 2024-09-18 | Closed | Closed Late (>2 Months) | 2024-12-17 | PKG2A(IJM) | Manpower | IJMC | 181
213 | RTS-MRTS-PKG2A-ICQC-NCR-000024 | Safety | NCR CHESS - Monthly SHE Audit | 2024-03-21 | 2024-04-04 | 2024-05-29 | After 14 days | 2024-10-06 | 2024-04-10 | Closed | Closed Late (>2 Months) | 2025-02-01 | PKG2A(IJM) | Internal process | IJMC | 20
214 | RTS-MRTS-PKG2-ICQC-NCR-000003 | Safety | NCR CHESS - Traffic Management Deliverables | 2024-03-22 | 2024-05-04 | 2024-05-15 | After 14 days | 2024-05-24 | 2024-07-06 | Closed | Closed Late (<2 Months) | 2024-05-09 | PKG2A(IJM) | Traffic | IJMC | 106
215 | RTS-MRTS-PKG2-ICQC-NCR-000002 | Safety | NCR CHESS - Security Training | 2024-03-22 | 2024-05-04 | 2024-04-18 | After 14 days | 2024-04-25 | 2024-04-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Security | IJMC | 38
216 | RTS-MRTS-PKG2-ICQC-NCR-000001 | Safety | NCR CHESS - Security Manager | 2024-03-22 | 2024-05-04 | 2024-04-18 | After 14 days | 2024-04-25 | 2024-04-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Security | IJMC | 38
220 | RTS-MRTS-PKG2A-ICQC-NCR-000026 | Env | Waste Management - Used chemical container was found mixed with construction waste in the scrap metal storage area. | 2024-03-22 | 2024-05-04 | 2024-03-25 | Within 14 days | 2024-01-04 | 2024-03-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Schedule waste management | IJMC | 7
221 | RTS-MRTS-PKG2A-ICQC-NCR-000025 | Env | Chemical Management - spillage of petroleum-based products not managed as scheduled waste. | 2024-03-22 | 2024-05-04 | 2024-03-25 | Within 14 days | 2024-01-04 | 2024-03-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG2A(IJM) | Schedule waste management | IJMC | 7
222 | RTS-MRTS-PKG2B-OVPR-NCR-000001 | Quality | Potential occurrence of cold joints between two cast of concrete. | 2024-03-04 | 2024-04-17 | 2024-06-04 | Within 14 days | 2024-04-26 | 2024-04-26 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG2B(IJM) | Workmanship | IJMC | 53
223 | RTS-MRTS-PKG2B-ICQC-NCR-000001 | Quality | MC30 P9 Column Verticality Out of Tolerance | 2024-03-04 | 2024-04-17 | 2024-04-19 | After 14 days | 2024-10-05 | 2024-05-23 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG2B(IJM) | Workmanship | IJMC | 80
224 | RTS-MRTS-GENE-OVPR-NCR-000064 | Safety | failed to provide and maintained sufficient numbers of Safety, Health and Environmental personnel | 2024-04-04 | 2024-04-18 | 2024-04-16 | Within 14 days | 2024-06-30 | 2024-10-02 | Closed | Closed Late (>2 Months) | 2024-12-31 | GENE- | Manpower | APSB | 181
225 | RTS-MRTS-GENE-OVPR-NCR-000065 | Env | Control of Substances Hazardous to Health | 2024-04-04 | 2024-04-18 | 2024-04-18 | Within 14 days | 2024-09-27 | 2024-09-26 | Closed | Closed on Time | 2024-12-25 | GENE- | Environment Control | APSB | 175
226 | RTS-MRTS-PKG3-VIAD-NCR-000021 | Safety | Working at Height - no fall prevention system | 2024-04-04 | 2024-04-18 | 2024-04-16 | Within 14 days | 2024-03-05 | 2024-04-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG3- | Safety Control | APSB | 25
227 | RTS-MRTS-PKG3-VIAD-NCR-000022 | Safety | [Security] Controlling and Monitoring Border | 2024-04-04 | 2024-04-18 | 2024-05-04 | Within 14 days | 2024-04-18 | 2024-08-05 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG3- | Security | APSB | 123
228 | RTS-MRTS-PKG6-WAHD-NCR-000027 | Safety | [Security] Appointment of Security Personnel at Site | 2024-04-04 | 2024-04-18 | 2024-04-19 | After 14 days | 2024-04-30 | 2024-04-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG6- | Security | APSB | 25
229 | RTS-MRTS-PKG6-WAHD-NCR-000028 | Env | TSS Exceed Limit | 2024-04-04 | 2024-04-18 | 2024-04-15 | Within 14 days | 2024-04-30 | 2024-04-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG6- | TSS reading | APSB | 25
230 | RTS-MRTS-PKG6-WAHD-NCR-000029 | Env | Scheduled Waste Storage | 2024-04-04 | 2024-04-18 | 2024-08-04 | Within 14 days | 2024-04-29 | 2024-04-29 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG6- | Schedule waste management | APSB | 25
231 | RTS-MRTS-PKG5-VIAD-NCR-000056 | Env | Muddy Water Direct Discharge into Public Drain | 2024-04-04 | 2024-04-18 | 2024-05-04 | Within 14 days | 2024-03-05 | 2024-06-05 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | PKG5- | Environment Control | SUNCON | 62
232 | RTS-MRTS-PKG3-VIAD-NCR-000023 | Safety | Safety & Health – handmade Ladders | 2024-04-23 | 2024-07-05 | 2024-04-25 | Within 14 days | 2024-05-24 | 2024-05-24 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG3- | Safety Control | APSB | 31
233 | RTS-MRTS-GENE-OVPR-NCR-000066 | Env | The non-compliances observed for the Noise and Vibration Control Plan (NVCP) Rev02 | 2024-04-05 | 2024-04-19 | 2024-04-15 | Within 14 days | 2024-04-26 | 2024-04-29 | Closed | Closed Late (<2 Months) | Refer NCR Analysis Sep'24 | GENE- | Documentation | APSB | 24
234 | RTS-MRTS-PKG5-VIAD-NCR-000054 | Safety | non-conformities were observed during the hoisting and lifting operations | 2024-04-17 | 2024-01-05 | 2024-04-24 | Within 14 days | 2024-05-31 | 2024-05-24 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Machinery and equipment | SUNCON | 37
235 | RTS-MRTS-PKG5-VIAD-NCR-000055 | Safety | non-conformities were observed during the working at height and scaffolds | 2024-04-17 | 2024-01-05 | 2024-04-25 | Within 14 days | 2024-05-31 | 2024-05-24 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG5- | Safety Control | SUNCON | 37
236 | RTS-MRTS-PKG2A-ICQC-NCR-000027 | Quality | Cofferdam 32 BP55 – Rebar Missing. No rebar cage was found during the hacking of BP55 to cut off level (COL) | 2024-04-30 | 2024-05-14 | 2024-05-13 | Within 14 days | 2024-05-24 | 2024-05-24 | Closed | Closed on Time | Refer NCR Analysis Sep'24 | PKG2A | Workmanship | APSB | 24
237 | RTS-MRTS-PKG3-VIAD-NCR-000024 | Quality | excess strand for Tendon T1 & T2 for both sides had been cropped without any approval | 2024-07-05 | 2024-05-21 | 2024-06-06 | After 14 days | 2024-06-30 | 2024-08-08 | Closed | Closed Late (<2 Months) | 2024-06-11 | PKG3- | Work without approved document | APSB | 34
238 | RTS-MRTS-PKG2-ICQC-NCR-000004 | P&D | IJMC has failed to close the Baseline Programme from Code 2 to Code 1 within 14 days and prolonged delay | 2024-05-14 | 2024-05-28 | 2024-05-18 | Within 14 days | 2024-05-08 | 2024-07-17 | Closed | Closed on Time | 2024-10-15 | PKG2A(IJM) | Documentation | IJMC | 64
240 | RTS-MRTS-PKG3-VIAD-NCR-000026 | Safety | Ladder and barricade - no evidence of inspection conducted at temporary access ladder at pier 46 and pier 47. | 2024-05-17 | 2024-05-31 | 2024-05-28 | Within 14 days | 2024-06-14 | 2024-12-06 | Closed | Closed on Time | 2024-10-09 | PKG3- | Safety Control | APSB | 203
241 | RTS-MRTS-PKG5-VIAD-NCR-000057 | Safety | Scaffold and Falsework non compliance | 2024-05-23 | 2024-06-06 | 2024-04-06 | Within 14 days | 2024-07-31 | 2024-07-16 | Closed | Closed on Time | 2024-10-14 | PKG5- | Safety Control | SUNCON | 54
242 | RTS-MRTS-PKG5-VIAD-NCR-000058 | Safety | Working at height non compliance | 2024-05-23 | 2024-06-06 | 2024-04-06 | Within 14 days | 2024-07-31 | 2024-07-16 | Closed | Closed on Time | 2024-10-14 | PKG5- | Safety Control | SUNCON | 54
243 | RTS-MRTS-PKG4-BUCS-NCR-000031 | Env | Chemical handling and management | 2024-05-21 | 2024-04-06 | 2024-04-06 | Within 14 days | 2024-06-28 | 2024-07-02 | Closed | Closed Late (<2 Months) | 2024-09-30 | PKG4- | Environment Control | APSB | 42
244 | RTS-MRTS-PKG4-BUCS-NCR-000035 | Safety | NCR CHESS - SECURITY DOCUMENTATION AT PACKAGE 4. | 2024-06-11 | 2024-06-25 | 2024-06-20 | Within 14 days | 2024-08-26 | 2024-08-15 | Closed | Closed on Time | 2024-11-13 | PKG4- | Documentation | APSB | 65
245 | RTS-MRTS-PKG6-WAHD-NCR-000031 | Quality | QSA Audit - PKG6 TNB Room – LV cables submerged underneath the water ponding. | 2024-06-12 | 2024-06-26 | 2024-06-24 | Within 14 days | 2024-07-15 | 2024-10-01 | Closed | Closed Late (>2 Months) | 2024-12-30 | PKG6- | Workmanship | APSB | 111
246 | RTS-MRTS-PKG6-WAHD-NCR-000030 | Quality | QSA Audit - PKG6 TNB Room – Water Ponding Inside the Manhole. | 2024-06-12 | 2024-06-26 | 2024-06-25 | Within 14 days | 2024-07-15 | 2024-11-25 | Closed | Closed Late (>2 Months) | 2025-02-23 | PKG6- | Workmanship | APSB | 166
247 | RTS-MRTS-PKG4-BUCS-NCR-000034 | Quality | QSA Audit - PKG4 Battery Room - Corroded Bolt and Nut. | 2024-06-12 | 2024-06-26 | 2024-12-07 | After 14 days | 2024-07-31 | 2024-10-03 | Closed | Closed Late (>2 Months) | 2025-01-01 | PKG4- | Workmanship | APSB | 113
248 | RTS-MRTS-PKG4-BUCS-NCR-000033 | Quality | QSA Audit - PKG Poor Workmanship at Roller Shutter TNB SSU Area | 2024-06-12 | 2024-06-26 | 2024-06-27 | After 14 days | 2024-09-30 | 2024-11-25 | Closed | Closed Late (<2 Months) | 2025-02-23 | PKG4- | Workmanship | APSB | 166
249 | RTS-MRTS-PKG4-BUCS-NCR-000032 | Quality | QSA Audit - PKG4 Material Submission Approval (MSA) Anti Vermin Netting | 2024-06-12 | 2024-06-26 | 2024-06-21 | Within 14 days | 2024-06-30 | 2024-10-01 | Closed | Closed Late (>2 Months) | 2024-12-30 | PKG4- | Work without approved document | APSB | 111
250 | RTS-MRTS-PKG3-VIAD-NCR-000029 | Quality | QSA Audit - PKG3 Reference in Work Inspection Request (WIR). | 2024-06-12 | 2024-06-26 | 2024-06-24 | Within 14 days | 2024-09-30 | 2024-11-27 | Closed | Closed Late (<2 Months) | 2025-02-25 | PKG3- | Documentation | APSB | 168
251 | RTS-MRTS-PKG3-VIAD-NCR-000028 | Quality | QSA Audit - PKG3 No Evidence for Training F3 Mock up Finish has been conducted | 2024-12-06 | 2024-06-26 | 2024-06-24 | Within 14 days | 2024-07-30 | 2024-12-31 | Closed | Closed Late (>2 Months) | 2025-03-31 | PKG3- | Internal process | APSB | 25
252 | RTS-MRTS-PKG3-VIAD-NCR-000027 | Quality | QSA Audit - PKG3 No Material Identification Marking for Precast Skirting | 2024-06-12 | 2024-06-26 | 2024-06-24 | Within 14 days | 2024-07-20 | 2024-10-04 | Closed | Closed Late (>2 Months) | 2025-02-01 | PKG3- | Internal process | APSB | 114
255 | RTS-MRTS-PKG5-VIAD-NCR-000059 | Safety | NCR CHESS - Confined Space – Hand Dug Caisson CPP Wall | 2024-06-25 | 2024-09-07 | 2024-06-28 | Within 14 days | 2024-07-31 | 2024-11-10 | Closed | Closed Late (>2 Months) | 2025-09-01 | PKG5- | Safety Control | SUNCON | 138
256 | RTS-MRTS-PKG5-VIAD-NCR-000060 | Safety | NCR CHESS - Contractor’s Safety and Health Personnel | 2024-06-20 | 2024-04-07 | 2024-11-07 | After 14 days | 2024-08-31 | 2024-08-16 | Closed | Closed on Time | 2024-11-14 | PKG5- | Manpower | SUNCON | 57
259 | RTS-MRTS-PKG5-VIAD-NCR-000061 | Env | NCR CHESS - Discharge of Silted Groundwater | 2024-06-24 | 2024-08-07 | 2024-07-16 | After 14 days | 2024-07-23 | 2024-10-10 | Closed | Closed Late (>2 Months) | 2025-08-01 | PKG5- | Environment Control | SUNCON | 108
260 | RTS-MRTS-PKG3-VIAD-NCR-000030 | Quality | Exposed and Corroded Reinforcement on SBG (insufficient cover) | 2024-06-25 | 2024-09-07 | 2024-06-27 | Within 14 days | 2024-07-31 | 2024-10-02 | Closed | Closed Late (>2 Months) | 2024-12-31 | PKG3- | Workmanship | APSB | 99
261 | RTS-MRTS-PKG6-WAHD-NCR-000033 | Safety | NCR CHESS - SECURITY AT WADI HANA DEPOT | 2024-06-25 | 2024-09-07 | 2024-06-26 | Within 14 days | 2024-05-07 | 2024-07-02 | Closed | Closed on Time | 2024-09-30 | PKG6- | Security | APSB | 7
262 | RTS-MRTS-PKG2-ICQC-NCR-000008 | Quality | NCR QAQC - Material Delivery Inspection (Audit No. 1) | 2024-06-25 | 2024-09-07 | 2024-09-07 | Within 14 days | 2024-08-15 | 2024-08-15 | Closed | Closed on Time | 2024-11-13 | PKG2A(IJM) | Inspection | IJMC | 51
263 | RTS-MRTS-PKG2-ICQC-NCR-000007 | Quality | NCR QAQC - Inspection and Testing (Audit No. 1) | 2024-06-25 | 2024-09-07 | 2024-09-07 | Within 14 days | 2024-09-21 | 2024-09-21 | Closed | Closed on Time | 2024-12-20 | PKG2A(IJM) | Inspection | IJMC | 88
264 | RTS-MRTS-PKG2-ICQC-NCR-000006 | Quality | NCR QAQC - Work Inspection Request (Audit No. 1) | 2024-06-25 | 2024-09-07 | 2024-09-07 | Within 14 days | 2024-09-30 | 2024-09-27 | Closed | Closed on Time | 2024-12-26 | PKG2A(IJM) | Inspection | IJMC | 94
265 | RTS-MRTS-PKG2-ICQC-NCR-000005 | Quality | NCR QAQC - Project Quality Plan (Audit No. 1) | 2024-06-25 | 2024-09-07 | 2024-08-07 | Within 14 days | 2024-10-18 | 2024-11-14 | Closed | Closed Late (<2 Months) | 2025-12-02 | PKG2A(IJM) | Documentation | IJMC | 142
267 | RTS-MRTS-PKG2A-ICQC-NCR-000029 | Quality | Soil had settled below the key beam at GL QC-QD/Q4-Q5 due to improper compaction | 2024-07-17 | 2024-07-31 | 2024-07-31 | Within 14 days | 2024-09-13 | 2024-09-19 | Closed | Closed Late (<2 Months) | 2024-12-18 | PKG2A(IJM) | Workmanship | IJMC | 64
268 | RTS-MRTS-PKG2A-ICQC-NCR-000028 | Safety | electrical cables was placed in direct contact with galvanized iron (GI) pipes without non-conductive insulation | 2024-07-25 | 2024-08-08 | 2024-08-28 | After 14 days | 2024-06-09 | 2024-10-03 | Closed | Closed Late (<2 Months) | 2025-01-01 | PKG2A(IJM) | Safety Control | IJMC | 70
269 | RTS-MRTS-PKG4-BUCS-NCR-000036 | Safety | NCR CHESS - Safety & Health (Working at Height) | 2024-09-08 | 2024-08-23 | 2024-08-26 | After 14 days | 2024-09-20 | 2024-09-19 | Closed | Closed on Time | 2024-12-18 | PKG4- | Safety Control | APSB | 11
270 | RTS-MRTS-PKG5-VIAD-NCR-000062 | Safety | Incomplete edge protection and portal without a fall prevention system a | 2024-08-15 | 2024-08-29 | 2024-08-22 | Within 14 days | 2024-10-14 | 2024-10-10 | Closed | Closed on Time | 2025-08-01 | PKG5- | Safety Control | SUNCON | 56
271 | RTS-MRTS-PKG8-BUCS-NCR-000001 | Quality | Damage and corrosion on the primer surfaces of X-Frame after lifting work at the fabrication yard. | 2024-08-16 | 2024-08-30 | 2024-08-27 | Within 14 days | 2024-10-09 | 2024-09-19 | Closed | Closed Late (<2 Months) | 2024-12-18 | PKG8- | Workmanship | ROHAS | 34
272 | RTS-MRTS-PKG5-VIAD-NCR-000064 | Safety | non-compliance related to drainage activities | 2024-08-29 | 2024-12-09 | 2024-03-09 | Within 14 days | 2024-10-16 | 2024-10-10 | Closed | Closed on Time | 2025-08-01 | PKG5- | Safety Control | SUNCON | 42
273 | RTS-MRTS-PKG5-VIAD-NCR-000063 | Safety | non-compliance related to work at height activities that poses a significant safety risk | 2024-08-29 | 2024-12-09 | 2024-03-09 | Within 14 days | 2024-10-18 | 2024-10-10 | Closed | Closed on Time | 2025-08-01 | PKG5- | Safety Control | SUNCON | 42
274 | RTS-MRTS-PKG3-VIAD-NCR-000031 | Safety | Safety & Health (Hoisting and Lifting Operations) | 2024-08-29 | 2024-12-09 | 2024-12-09 | Within 14 days | 2024-04-10 | 2024-09-19 | Closed | Closed on Time | 2024-12-18 | PKG3- | Safety Control | APSB | 21
275 | RTS-MRTS-PKG8-BUCS-NCR-000002 | Quality | QA Audit - Work Inspection Request was not accurately maintained in terms of its accuracy of reference number, and its completeness for closure. | 2024-03-09 | 2024-09-17 | 2024-09-09 | Within 14 days | 2024-09-13 | 2024-09-13 | Closed | Closed on Time | 2024-12-12 | PKG8- | Documentation | ROHAS | 188
276 | RTS-MRTS-PKG8-BUCS-NCR-000003 | Quality | QA Audit - Unable to provide sufficient and relevant documented for internal quality audit. | 2024-03-09 | 2024-09-17 | 2024-09-17 | Within 14 days | 2024-01-11 | 2024-11-14 | Closed | Closed Late (<2 Months) | 2025-12-02 | PKG8- | Documentation | ROHAS | 250
277 | RTS-MRTS-PKG8-BUCS-NCR-000004 | Quality | QA Audit - No evidence material testing for sampling was conducted after more than a month of material inspection | 2024-03-09 | 2024-09-17 | 2024-09-09 | Within 14 days | 2024-09-13 | 2024-09-13 | Closed | Closed on Time | 2024-12-12 | PKG8- | Inspection | ROHAS | 188
278 | RTS-MRTS-PKG5-VIAD-NCR-000065 | Safety | Method Statement and HIRARC for the LG truss assembly was not submitted to MRTS before the work commenced | 2024-05-09 | 2024-09-19 | 2024-09-09 | Within 14 days | 2024-11-10 | 2024-08-10 | Closed | Closed on Time | 2025-06-01 | PKG5- | Documentation | SUNCON | 93
279 | RTS-MRTS-PKG2A-ICQC-NCR-000030 | Env | NCR CHESS - Insufficient Implementation of Vector Measures | 2024-04-10 | 2024-10-18 | 2024-12-10 | Within 14 days | 2024-10-25 | 2024-11-12 | Closed | Closed Late (<2 Months) | 2025-11-03 | PKG2A(IJM) | Environment Control | IJMC | 216
280 | RTS-MRTS-PKG2A-ICQC-NCR-000034 | Safety | NCR CHESS CIGARETTE BUTTS | 2024-04-10 | 2024-10-18 | 2024-10-18 | Within 14 days | 2024-12-16 | 2024-11-12 | Closed | Closed on Time | 2025-11-03 | PKG2A(IJM) | Safety Control | IJMC | 216
281 | RTS-MRTS-PKG5-VIAD-NCR-000066 | Safety | NCR CHESS - Chemical Storage | 2024-10-03 | 2024-10-17 | 2024-11-10 | Within 14 days | 2024-11-12 | 2024-12-02 | Closed | Closed on Time | 2025-02-03 | PKG5- | Environment Control | SUNCON | 60
282 | RTS-MRTS-PKG5-VIAD-NCR-000067 | Safety | NCR CHESS - Unsafe Access, No Ladder Inspection, Damaged Ladder & No Edge Protection | 2024-03-10 | 2024-10-17 | 2024-11-10 | Within 14 days | 2024-11-27 | 2024-11-27 | Closed | Closed on Time | 2025-02-25 | PKG5- | Safety Control | SUNCON | 262
283 | RTS-MRTS-PKG2A-ICQC-NCR-000033 | Quality | Construction Joint Surface | 2024-02-10 | 2024-10-16 | 2024-09-10 | Within 14 days | 2024-11-13 | 2024-06-11 | Closed | Closed on Time | 2025-04-02 | PKG2A(IJM) | Workmanship | IJMC | 122
284 | RTS-MRTS-PKG5-VIAD-NCR-000070 | Env | NCR CHESS - Environmental Deliverables | 2024-02-10 | 2024-10-16 | 2024-07-10 | Within 14 days | 2024-11-27 | 2024-04-12 | Closed | Closed Late (<2 Months) | 2025-04-03 | PKG5- | Documentation | SUNCON | 62
287 | RTS-MRTS-PKG2-ICQC-NCR-000009 | Safety | NCR CHESS - Pending Submission of SHE Deliverables | 2024-09-26 | 2024-10-10 | 2024-11-10 | After 14 days | 2024-10-21 | 2024-10-21 | Closed | Closed on Time | 2025-01-19 | PKG2A(IJM) | Documentation | IJMC | 25
288 | RTS-MRTS-PKG2-ICQC-NCR-000010 | Safety | NCR CHESS - No Safety and Health Personnels During Night Works Activity | 2024-09-25 | 2024-09-10 | 2024-01-10 | Within 14 days | 2024-10-14 | 2024-10-07 | Closed | Closed on Time | 2025-05-01 | PKG2A(IJM) | Safety Control | IJMC | 12
289 | RTS-MRTS-PKG6-WAHD-NCR-000035 | Safety | CHESS NCR - Safety & Health (Fire Prevention and Hot Work) | 2024-09-10 | 2024-10-23 | 2024-10-17 | Within 14 days | 2024-01-11 | 2024-10-23 | Closed | Closed on Time | 2025-01-21 | PKG6- | Safety Control | APSB | 43
290 | RTS-MRTS-PKG3-VIAD-NCR-000032 | Safety | CHESS NCR - Safety & Health (Working at Height) | 2024-09-10 | 2024-10-23 | 2024-10-21 | Within 14 days | 2024-08-11 | 2024-10-23 | Closed | Closed on Time | 2025-01-21 | PKG3- | Safety Control | APSB | 43
291 | RTS-MRTS-PKG3-VIAD-NCR-000033 | Safety | CHESS NCR - Safety & Health (Illumination and Ventilation) | 2024-09-10 | 2024-10-23 | 2024-10-22 | Within 14 days | 2024-08-11 | 2024-10-23 | Closed | Closed on Time | 2025-01-21 | PKG3- | Safety Control | APSB | 43
294 | RTS-MRTS-PKG4-BUCS-NCR-000037 | Safety | Housekeeping, Sanitary and Welfare Facilities | 2024-11-10 | 2024-10-25 | 2024-10-23 | Within 14 days | 2024-11-25 | 2024-12-11 | Closed | Closed on Time | 2025-10-02 | PKG4- | Safety Control | APSB | 31
295 | RTS-MRTS-PKG2A-ICQC-NCR-000036 | Quality | Poor workmanship was observed on floor hardener finishes during the inspection at trenches in Consumer HT Room. | 2024-10-18 | 2024-01-11 | 2024-01-11 | Within 14 days | 2024-01-12 | 2024-11-25 | Closed | Closed on Time | 2025-02-23 | PKG2A(IJM) | Workmanship | IJMC | 38
297 | RTS-MRTS-PKG2A-ICQC-NCR-000035 | Safety | NCR CHESS - Unauthorized Rest Area at Site | 2024-10-23 | 2024-06-11 | 2024-11-21 | After 14 days | 2024-06-11 | 2024-12-05 | Closed | Closed Late (<2 Months) | 2025-05-03 | PKG2A(IJM) | Safety Control | IJMC | 43
298 | RTS-MRTS-PKG4-BUCS-NCR-000046 | Env | NCR CHESS - Waste Management | 2024-10-23 | 2024-06-11 | 2024-10-30 | Within 14 days | 2024-12-25 | 2024-12-25 | Closed | Closed on Time | 2025-03-25 | PKG4- | Schedule waste management | APSB | 63
299 | RTS-MRTS-GENE-OVPR-NCR-000073 | Safety | NCR CHESS - CLQ Management Plan, no provision of yearly training conducted | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2024-12-20 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | GENE- | Internal process | APSB | 58
300 | RTS-MRTS-GENE-OVPR-NCR-000075 | Safety | NCR CHESS - Incident Notification, Investigation and Reporting | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2024-12-27 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | GENE- | Documentation | APSB | 58
301 | RTS-MRTS-PKG4-BUCS-NCR-000047 | Safety | NCE CHESS - Security Management Plan | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2024-12-24 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | PKG4- | Security | APSB | 58
302 | RTS-MRTS-GENE-OVPR-NCR-000072 | Env | NCR CHESS - Monthly Environmental Audit Plan and Report | 2024-10-23 | 2024-06-11 | 2024-10-29 | Within 14 days | 2024-12-17 | 2024-12-25 | Closed | Closed Late (<2 Months) | 2025-03-25 | GENE- | Documentation | APSB | 63
303 | RTS-MRTS-PKG4-BUCS-NCR-000045 | Safety | NCR CHESS - Temporary Electrical Installation at Site | 2024-10-23 | 2024-06-11 | 2024-05-11 | Within 14 days | 2025-01-17 | 2025-01-17 | Closed | Closed on Time |  | PKG4- | Manpower | APSB | 86
304 | RTS-MRTS-PKG4-BUCS-NCR-000043 | Safety | NCR CHESS - Scaffolds | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2024-12-20 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | PKG4- | Safety Control | APSB | 58
306 | RTS-MRTS-PKG4-BUCS-NCR-000040 | Safety | NCR CHESS - Training and Competencies | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2025-03-01 | 2025-01-27 | Closed | Closed Late (<2 Months) |  | PKG4- | Internal process | APSB | 96
307 | RTS-MRTS-PKG4-BUCS-NCR-000039 | Safety | NCR CHESS - Working at Height | 2024-10-23 | 2024-06-11 | 2024-06-11 | Within 14 days | 2025-03-01 | 2024-12-25 | Closed | Closed on Time | 2025-03-25 | PKG4- | Safety Control | APSB | 63
308 | RTS-MRTS-PKG4-BUCS-NCR-000038 | Env | NCR CHESS - Dirty Public Road | 2024-10-22 | 2024-05-11 | 2024-10-29 | Within 14 days | 2024-12-18 | 2024-12-18 | Closed | Closed on Time | 2025-03-18 | PKG4- | Environment Control | APSB | 57
310 | RTS-MRTS-PKG2A-ICQC-NCR-000037 | Safety | cigarette butts left by the workers smoking within the construction area | 2024-04-11 | 2024-11-18 | 2024-11-20 | After 14 days | 2024-06-11 | 2024-11-12 | Closed | Closed Late (<2 Months) | 2025-11-03 | PKG2A(IJM) | Safety Control | IJMC | 215
311 | RTS-MRTS-PKG2A-ICQC-NCR-000038 | Safety | cigarette butts left by the workers smoking within the construction area | 2024-04-11 | 2024-11-18 | 2024-11-20 | After 14 days | 2024-06-11 | 2024-11-12 | Closed | Closed Late (<2 Months) | 2025-11-03 | PKG2A(IJM) | Safety Control | IJMC | 215
312 | RTS-MRTS-PKG2A-ICQC-NCR-000039 | Safety | cigarette butts left by the workers smoking within the construction area | 2024-04-11 | 2024-11-18 | 2024-11-20 | After 14 days | 2024-06-11 | 2024-11-12 | Closed | Closed Late (<2 Months) | 2025-11-03 | PKG2A(IJM) | Safety Control | IJMC | 215
313 | RTS-MRTS-PKG2A-ICQC-NCR-000040 | Safety | cigarette butts left by the workers smoking within the construction area | 2024-04-11 | 2024-11-18 | 2024-11-20 | After 14 days | 2024-06-11 | 2024-11-12 | Closed | Closed Late (<2 Months) | 2025-11-03 | PKG2A(IJM) | Safety Control | IJMC | 215
315 | RTS-MRTS-PKG2B-ICQC-NCR-000002 | Quality | Major post concrete defects were observed for the Precast T-Beam span MC30 P6-P7 (beam mark BM3) such as major honeycomb and segregation in concrete, surface cracks with visible water seeping through, excessive pinholes and rough surface, and suspect of cold joint along the beam span. | 2024-11-14 | 2024-11-28 | 2024-11-20 | Within 14 days | 2024-10-12 | 2024-12-06 | Closed | Closed on Time | 2025-06-03 | PKG2B(IJM) | Workmanship | IJMC | 22
316 | RTS-MRTS-PKG5-VIAD-NCR-000072 | Safety | ​Roof Installation Work - Lifeline During the MRTS SHE Executive Site Walk conducted on 5 November 2024 at Zone 1, it was observed non-compliance related to installation of roof panel that poses a significant risk to workers as detailed below: 1. Failure to provide evidence of lifeline installed for roof installation work has been inspected and tested prior to use. 2. No provision of PE design calculations for the installed lifeline. 3. Unsafe termination of the wire rope which was secured with only two (2) bulldog clips and a nylon rope was observed being used as the lifeline connected to the wire rope. 4. Observed worker hook the harness to the extended lifeline to the end loop of the wire rope. | 2024-11-13 | 2024-11-27 | 2024-11-21 | Within 14 days | 2024-05-12 | 2024-12-05 | Closed | Closed on Time | 2025-05-03 | PKG5- | Safety Control | SUNCON | 22
317 | RTS-MRTS-PKG5-VIAD-NCR-000073 | Env | Mosquito Larvae Breeding During the MRTS SHE Executive Site Walk conducted on 5 November 2024 at Zone 1, mosquito larvae breeding was observed in most of the water-filled holes. Larviciding should be carried out and the holes should be sealed. | 2024-11-13 | 2024-11-27 | 2024-11-21 | Within 14 days | 2024-05-12 | 2024-12-05 | Closed | Closed on Time | 2025-05-03 | PKG5- | Environment Control | SUNCON | 22
318 | RTS-MRTS-PKG6-WAHD-NCR-000037 | Safety | DESCRIPTION OF NON-CONFORMITY: Safety & Health (Laws, Regulations, Order, Code of Practice, Guidelines and Standards) During the Executive site walk conducted on 06 November 2024 by MRTS at Wadihana Depoh Package 6 it was observed that workers with expired / no record at CIDB green card. B. | 2024-11-11 | 2024-11-25 | 2024-11-26 | After 14 days | 2024-12-27 | 2024-12-25 | Closed | Closed on Time | 2025-03-25 | PKG6- | Safety Control | APSB | 44
319 | RTS-MRTS-PKG6-WAHD-NCR-000036 | Safety | Scaffold access to the OSD tank is without scaffold drawing and PIC detail. The scaffold access is due for inspection last inspected was on 12 October 2024. Scaffold access to OSD working area was not inspected and no green tag attached. Scaffold access without drawing and PIC detail. Scaffold access at track level toward roof level is due for inspection. Last inspection was conducted on 28 October 2024. Working platform for conducting brick laying work without scaffold drawing and PIC detail. No SWL attached at working platform to identified the load capacity allowed to be stack on the working platform. Reference: 1. GS G23.11 (1 - 15) Scaffolds | 2024-11-11 | 2024-11-25 | 2024-11-26 | After 14 days | 2024-12-20 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | PKG6- | Safety Control | APSB | 39
322 | RTS-MRTS-PKG5-VIAD-NCR-000075 | Safety | NCR CHESS - Working at Height (Zone 2) | 2024-11-21 | 2024-05-12 | 2024-11-23 | Within 14 days | 2024-12-31 | 2024-12-31 | Closed | Closed on Time | 2025-03-31 | PKG5- | Safety Control | SUNCON | 40
323 | RTS-MRTS-PKG5-VIAD-NCR-000074 | Safety | NCR CHESS - RWDP Installation | 2024-11-21 | 2024-05-12 | 2024-11-23 | Within 14 days | 2024-12-25 | 2024-12-20 | Closed | Closed on Time | 2025-03-20 | PKG5- | Safety Control | SUNCON | 29
324 | RTS-MRTS-PKG5-VIAD-NCR-000076 | Safety | NCR CHESS - Drainage work (Excavation) | 2024-11-21 | 2024-05-12 | 2024-09-12 | After 14 days | 2024-12-25 | 2025-07-02 | Closed | Closed Late (<2 Months) |  | PKG5- | Safety Control | SUNCON | 223
326 | RTS-MRTS-PKG4-BUCS-NCR-000052 | Safety | CHESS NCR - Safety & Health – Housekeeping, Sanitary and Welfare Facilities | 2024-11-25 | 2024-09-12 | 2024-11-12 | After 14 days | 2025-01-17 | 2025-03-01 | Closed | Closed on Time |  | PKG4- | Safety Control | APSB | 96
327 | RTS-MRTS-PKG4-BUCS-NCR-000053 | Safety | NCR CHESS - Safety & Health (Laws, Regulations, Order, Code of Practice, Guidelines and Standards) observed that workers with expired / no record at CIDB green card | 2024-11-25 | 2024-09-12 | 2024-11-12 | After 14 days | 2025-01-17 | 2025-03-01 | Closed | Closed on Time |  | PKG4- | Safety Control | APSB | 96
328 | RTS-MRTS-PKG6-WAHD-NCR-000039 | Safety | CHESS NCR - Safety & Health (Performing High Risk Tasks) | 2024-11-25 | 2024-09-12 | 2024-10-12 | After 14 days | 2024-12-27 | 2025-01-17 | Closed | Closed Late (<2 Months) |  | PKG6- | Safety Control | APSB | 53
330 | RTS-MRTS-PKG4-BUCS-NCR-000051 | Safety | NCR CHESS - Erosion and Sedimentation Control Package 4 | 2024-11-26 | 2024-10-12 | 2024-11-28 | Within 14 days | 2024-12-25 | 2025-06-01 | Closed | Closed Late (<2 Months) |  | PKG4- | Environment Control | APSB | 187
331 | RTS-MRTS-PKG3-VIAD-NCR-000034 | Safety | NCR CHESS - Scheduled Waster (SW) Storage | 2024-11-27 | 2024-11-12 | 2024-10-12 | Within 14 days | 2024-12-31 | 2025-06-01 | Closed | Closed Late (<2 Months) |  | PKG3- | Schedule waste management | APSB | 186
332 | RTS-MRTS-PKG2A-ICQC-NCR-000041 | Safety | NCR CHESS - Unsecured Scaffold | 2024-11-27 | 2024-11-12 | 2024-12-20 | After 14 days | 2025-06-01 | 2025-02-01 | Closed | Closed on Time |  | PKG2A(IJM) | Safety Control | IJMC | 66
333 | RTS-MRTS-PKG2A-ICQC-NCR-000042 | Safety | NCR CHESS - MISSING TOE BOARD | 2024-11-27 | 2024-11-12 | 2024-12-20 | After 14 days | 2025-06-01 | 2025-02-01 | Closed | Closed on Time |  | PKG2A(IJM) | Safety Control | IJMC | 66
334 | RTS-MRTS-PKG2A-ICQC-NCR-000043 | Safety | NCR CHESS - Improper Access Walkway | 2024-11-27 | 2024-11-12 | 2024-12-20 | After 14 days | 2025-06-01 | 2025-02-17 | Closed | Closed Late (<2 Months) |  | PKG2A(IJM) | Safety Control | IJMC | 82
335 | RTS-MRTS-PKG6-WAHD-NCR-000040 | Safety | CHESS NCR - Safety & Health – Housekeeping, Sanitary and Welfare Facilities | 2024-02-12 | 2024-12-16 | 2024-12-16 | Within 14 days | 2024-12-27 | 2024-12-25 | Closed | Closed on Time | 2025-03-25 | PKG6- | Safety Control | APSB | 317
336 | RTS-MRTS-PKG2A-ICQC-NCR-000044 | Safety | NCR CHESS - Ignition Source in Chemical Store | 2024-02-12 | 2024-12-16 | 2024-12-30 | After 14 days | 2025-06-01 | 2025-05-02 | Closed | Closed Late (<2 Months) |  | PKG2A(IJM) | Safety Control | IJMC | 445
337 | RTS-MRTS-PKG2A-ICQC-NCR-000045 | Env | It was sighted that the muddy water in Silt Trap 4 (ST4) has exceeded the height of the pipe riser. This resulted in unfiltered overflow of muddy water and discharged directly into the public drain. | 2024-02-12 | 2024-12-16 | 2024-04-12 | Within 14 days | 2024-12-16 | 2024-12-16 | Closed | Closed on Time | 2025-03-16 | PKG2A(IJM) | Environment Control | IJMC | 308
338 | RTS-MRTS-PKG5-VIAD-NCR-000077 | Quality | NCR QAQC - Mock-up for Inspection Track | 2024-04-12 | 2024-12-18 | 2024-07-12 | Within 14 days | 2025-01-31 | 2025-01-27 | Closed | Closed on Time |  | PKG5- | Inspection | SUNCON | 290
340 | RTS-MRTS-PKG5-VIAD-NCR-000079 | Quality | NCR QAQC - Material Storage for Louvre | 2024-04-12 | 2024-12-18 | 2024-07-12 | Within 14 days | 2024-12-14 | 2024-12-30 | Closed | Closed Late (<2 Months) |  | PKG5- | Workmanship | SUNCON | 262
344 | RTS-MRTS-PKG5-VIAD-NCR-000083 | Quality | NCR QAQC - Test Equipment Register | 2024-04-12 | 2024-12-18 | 2024-10-12 | Within 14 days | 2024-12-28 | 2025-02-20 | Closed | Closed Late (<2 Months) |  | PKG5- | Documentation | SUNCON | 314
345 | RTS-MRTS-PKG5-VIAD-NCR-000084 | Quality | NCR QAQC - Internal Quality Audit Plan | 2024-04-12 | 2024-12-18 | 2024-12-12 | Within 14 days | 2024-12-31 | 2025-01-17 | Closed | Closed Late (<2 Months) |  | PKG5- | Documentation | SUNCON | 280
346 | RTS-MRTS-PKG6-WAHD-NCR-000041 | Safety | NCR CHESS : Scheduled Waste (SW) Storage and Chemical Storage | 2024-10-12 | 2024-12-24 | 2024-12-20 | Within 14 days | 2025-01-24 | 2025-01-21 | Closed | Closed on Time |  | PKG6- | Schedule waste management | APSB | 101
347 | RTS-MRTS-PKG8-BUCS-NCR-000007 | Safety | NCR CHESS - Safety & Health (Hoisting and Lifting Operations) | 2024-12-17 | 2024-12-31 | 2024-12-24 | Within 14 days | 2024-12-30 | 2025-01-17 | Closed | Closed Late (<2 Months) |  | PKG8- | Safety Control | ROHAS | 31
348 | RTS-MRTS-PKG8-BUCS-NCR-000006 | Safety | CHESS NCR - Safety & Health (Hoisting and Lifting Operations) | 2024-12-17 | 2024-12-31 | 2025-12-24 | After 14 days | 2025-01-20 | 2025-01-27 | Closed | Closed Late (<2 Months) |  | PKG8- | Safety Control | ROHAS | 41
349 | RTS-MRTS-PKG8-BUCS-NCR-000008 | Safety | NCR CHESS - Safety & Health – Control of Noise | 2024-12-17 | 2024-12-31 | 2024-12-24 | Within 14 days | 2024-12-31 | 2025-01-17 | Closed | Closed Late (<2 Months) |  | PKG8- | Safety Control | ROHAS | 31
350 | RTS-MRTS-PKG4-BUCS-NCR-000055 | Safety | CHESS NCR - Safety & Health – Safe Access | 2024-12-17 | 2024-12-31 | 2024-12-31 | Within 14 days | 2025-01-21 | 2025-01-17 | Closed | Closed on Time |  | PKG4- | Safety Control | APSB | 31
351 | RTS-MRTS-PKG5-VIAD-NCR-000085 | Safety | NCR CHESS - PUBLIC TRESPASSING | 2024-12-17 | 2024-12-31 | 2024-12-27 | Within 14 days | 2025-01-22 | 2025-01-15 | Closed | Closed on Time |  | PKG5- | Safety Control | SUNCON | 29
352 | RTS-MRTS-PKG2B-ICQC-NCR-000004 | Safety | NCR CHESS - Lifting Gear | 2024-12-18 | 2025-01-01 | 2025-01-16 | After 14 days | 2025-01-24 | 2025-01-24 | Closed | Closed on Time |  | PKG2B(IJM) | Safety Control | IJMC | 37
353 | RTS-MRTS-PKG2B-ICQC-NCR-000005 | Safety | NCR CHESS - HDD Work Activity | 2024-12-18 | 2025-01-01 | 2025-01-16 | After 14 days | 2025-01-24 | 2025-01-24 | Closed | Closed on Time |  | PKG2B(IJM) | Safety Control | IJMC | 37
354 | RTS-MRTS-PKG2B-ICQC-NCR-000006 | Safety | NCR CHESS - Chemical Handling | 2024-12-18 | 2025-01-01 | 2025-01-16 | After 14 days | 2025-02-14 | 2025-10-02 | Closed | Closed on Time |  | PKG2B(IJM) | Environment Control | IJMC | 288
355 | RTS-MRTS-PKG2B-ICQC-NCR-000003 | Safety | NCR CHESS - Muddy water discharged out of site boundary | 2024-02-12 | 2024-12-16 | 2024-04-12 | Within 14 days | 2024-12-16 | 2024-12-16 | Closed | Closed on Time | 2025-03-16 | PKG2B(IJM) | Environment Control | IJMC | 308
356 | RTS-MRTS-PKG4-BUCS-NCR-000054 | Safety | CHESS NCR - Safety & Health – Housekeeping, Sanitary and Welfare Facilities | 2024-02-12 | 2024-12-16 | 2024-07-12 | Within 14 days | 2024-12-27 | 2024-11-12 | Closed | Closed on Time | 2025-11-03 | PKG4- | Safety Control | APSB | 274
358 | RTS-MRTS-PKG5-VIAD-NCR-000086 | Env | recurring issues related to mosquito larvae breeding | 2024-12-20 | 2025-03-01 | 2024-12-27 | Within 14 days | 2025-01-22 | 2025-01-17 | Closed | Closed on Time |  | PKG5- | Environment Control | SUNCON | 28
359 | RTS-MRTS-PKG4-BUCS-NCR-000056 | Safety | CHESS NCR - Safety & Health - Scaffolds | 2024-12-27 | 2025-10-01 | 2025-08-01 | Within 14 days | 2025-01-21 | 2025-01-17 | Closed | Closed on Time |  | PKG4- |  | APSB | 21
364 | RTS-MRTS-PKG6-WAHD-NCR-000045 | Safety | CHESS NCR - Safety & Health – Training and Competencies | 2025-01-09 | 2025-01-23 | 2025-01-15 | Within 14 days | 2025-01-31 | 2025-01-27 | Closed | Closed on Time |  | PKG6- |  | APSB | 18
365 | RTS-MRTS-PKG6-WAHD-NCR-000046 | Safety | NCR CHESS - Safety & Health – Temporary Electrical Installation at Site | 2025-01-09 | 2025-01-23 | 2025-01-16 | Within 14 days | 2025-01-31 | 2025-01-27 | Closed | Closed on Time |  | PKG6- |  | APSB | 18
367 | RTS-MRTS-PKG6-WAHD-NCR-000047 | Safety | Waste scattered on ground without proper waste management | 2025-01-16 | 2025-01-30 | 2025-01-24 | Within 14 days | 2025-02-25 | 2025-02-21 | Closed | Closed on Time |  | PKG6- | Environment Control | APSB | 36
368 | RTS-MRTS-PKG2A-ICQC-NCR-000047 | Quality | Work carried out on 9 Jan 25 at AHU & Fan Room (GL Q3-Q4/QH-QJ) was not satisfactorily done according to the M&W | 2025-01-15 | 2025-01-29 | 2025-01-21 | Within 14 days | 2025-05-02 | 2025-01-24 | Closed | Closed on Time |  | PKG2A(IJM) | Workmanship | IJMC | 9
369 | RTS-MRTS-PKG2A-ICQC-NCR-000048 | Safety | Two (2) workers were operating the scissor lift (Unit No: SL08037) at the site has not attended required grey card training on working on Mobile Elevated Work Platform | 2025-01-27 | 2025-10-02 | 2025-08-02 | Within 14 days | 2025-02-17 | 2025-02-17 | Closed | Closed on Time |  | PKG2A(IJM) |  | IJMC | 21